## Bid Summary
| Example 3A |  |  |  |  | 1030800 |  | 1074217 | Total bid Amount
UPDATE VALUES IN YELLOW |  |  | *Some agencies use a special code to identify the Bid Schedule
|  |  | Code* | Bid Schedule |  | Total with margin | Overhead | Total with overhead | QTY | Unit | Unit cost | Subtotals | Notes
| Notes |  | A-1 | 1 | Mob/Demob - shall not exceed 5% | 457400 | 3946.3636 | 461347 | 1 | LS | 461347 |  |  | 525000 | 5% of assumed project cost
|  |  | A-1 | 2 | Environmental Compliance | 104200 | 3946.3636 | 108147 | 1 | LS | 108147
Bid date: | 2025-05-30 |  | A-1 | 3 | Traffic Controls | 52700 | 3946.3636 | 56647 | 1 | LS | 56647
Award date: | 2025-05-30 |  | A-1 | 4 | Landowner Coordination | 28300 | 3946.3636 | 32247 | 1 | LS | 32247
Notice date: | 2025-07-15 |  | A-1 | 5 | Develop and Provide Water Supply | 54900 | 3946.3636 | 58847 | 1 | LS | 58847
Start Date: | 2025-07-20 |  | A-1 | 6 | Construction Survey | 92800 | 3946.3636 | 96747 | 1 | LS | 96747
Complete by: | 2026-02-01 |  | A-1 | 7 | Stabilized Construction Entrance | 26400 | 3946.3636 | 30347 | 4 | EA | 7586.75
|  |  | A-1 | 8 | Potholing and Utility Coordination | 117000 | 3946.3636 | 120947 | 1 | LS | 120947
Work Days: | 196 | (including weekends) | A-1 | 9 | Clearing and Grubbing | 35100 | 3946.3636 | 39047 | 1 | LS | 39047
|  |  | A-1 | 10 | Site Restoration | 35100 | 3946.3636 | 39047 | 1 | LS | 39047
|  |  | A-1 | 11 | As-Built Project Documents | 26900 | 3946.3636 | 30847 | 1 | LS | 30847
| 1000 | Liquidated Damages ($/day) |  |  |  | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
| 43410 | Project Overhead to be dispersed |  |  |  | 0 | 0 | 0 | 1 |  | 0
| 11 | Number of Bid Items to spread overhead |  |  |  | 0 | 0 | 0 | 1 |  | 0
| 3946.3636 | Overhead $$ / site |  |  |  | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
| 4.041% | Overhead as a % of Total |  |  |  | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
[6 empty] | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 27 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 28 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 29 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 30 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 31 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 32 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 33 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 34 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 35 |  | 0 | 0 | 0 | 1 |  | 0
[7 empty] | 43410 | (check against Cell B21)

## Prevailing Wage
Step #1
Review the Plan Set and the Specifications to identify the type of work that will be done.
Step #2
Use this link to identify potential wage determinations for those jobs:
*Ensure you are in the correct county.
https://www.dir.ca.gov/oprl/2024-1/PWD/Determinations/Subtrades/jrnylist.html
Step #3
List the Classification as well as the corresponding wage determinations:
| Classification | Wage ($/hr) | Jobs/Tasks | Justification | Task Code (if used)
1 | Labor Lead | 74.69
2 | Laborer | 71.69
3 | Operator | 96.29
4 | Driver | 76.71
5 | Landscaper
6 | Pipe Fitter | 87.69
7 | Etc
8 | Etc
*For justification, see "Scope of Work Provisions" link in the wage determinations from the link above.
*Wage is non-overtime.

## Bid Schedule
Example 3A | [10 empty] | Crew Info
[11 empty] | 3 | multiplier (helpers to leadman)
[11 empty] | 8 | working hours per day
Bid # | Description | Quantity | Unit | Unit Price | Total | MARGIN | OUR COST | TOTAL COST | RESPONSIBLE PARTY |  |  |  | Category | Our Cost | Sale Price
[13 empty] | Overhead | 35660 | 43410
| Project OVERHEAD | Quantity | Unit | Unit Price | 43410 | 17.85% |  | 35660 | LAW | Margin |  |  | Mob/Demob | 375000 | 457400
| Bonding | 1 | EA | 39520 | 39520 | 18% | 32400 | 32400 | LAW | 18% | In-house |  | Labor | 202479.6 | 247300
| Insurance | 1 | EA | 1830 | 1830 | 18% | 1500 | 1500 | LAW | 22% | Material |  | Materials | 11000 | 14200
| Restrooms | 1 | Months | 0 | 0 | 18% | 0 | 0 | LAW | 18% | Subs |  | Equipment | 47600 | 58200
| Administrative | 1 | HR | 30 | 30 | 18% | 120 | 120 | LAW | 18% | Equipment |  | Subs | 115930 | 141600
| Project Management | 1 | HR | 100 | 100 | 18% | 70 | 70 | LAW | 18% | Other |  | Rental | 44550 | 54600
| Permitting/Submittal Support | 1 | HR | 100 | 100 | 18% | 70 | 70 | LAW |  |  |  | Fuel | 44640 | 57500
| PM Fuel | 1 | LS | 1830 | 1830 | 18% | 1500 | 1500 | LAW |  |  |  | Other | 0 | 0
| Travel/Hotels | 1 | Days | 0 | 0 | 18% | 0 | 0 | LAW
| Per Diem | 1 | Days | 0 | 0 | 18% | 0 | 0 | LAW |  |  |  | Subtotal | 876859.6 | 1074210
[14 empty] | 18.37% | Margin (back-calculated)
BID SCHEDULE ITEMS
1 | Mob/Demob - shall not exceed 5% | Quantity | Unit | Unit Price | 457400 |  | Our Cost | 375000 | [6 empty] | 197350.4
| Mobilization/Demobilization | 1 | EA | 457400 | 457400 | 18% | 375000 | 375000 |  | Labor Hrs | Labor days |  | Crew days | Crew weeks
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0 |  | 2580 | 322.5 |  | 80.625 | 16.125
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
Blank
2 | Environmental Compliance | Quantity | Unit | Unit Price | 104200 |  |  | 84694
| Labor | 1 | LS | 37600 | 37600 | 18% | 30784 | 30784
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 5900 | 5900 | 18% | 4800 | 4800
| Subcontractors | 1 | LS | 12100 | 12100 | 18% | 9900 | 9900
| Rental | 1 | LS | 33200 | 33200 | 18% | 27210 | 27210
| Fuel | 1 | LS | 15400 | 15400 | 22% | 12000 | 12000
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
0
3 | Traffic Controls | Quantity | Unit | Unit Price | 52700 |  |  | 43180.8
| Labor | 1 | LS | 28300 | 28300 | 18% | 23180.8 | 23180.8
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 24400 | 24400 | 18% | 20000 | 20000
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
4 | Landowner Coordination | Quantity | Unit | Unit Price | 28300 |  |  | 23138
| Labor | 1 | LS | 28300 | 28300 | 18% | 23138 | 23138
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
5 | Develop and Provide Water Supply | Quantity | Unit | Unit Price | 54900 |  |  | 43990.4
| Labor | 1 | LS | 14200 | 14200 | 18% | 11590.4 | 11590.4
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 17600 | 17600 | 18% | 14400 | 14400
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 23100 | 23100 | 22% | 18000 | 18000
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
6 | Construction Survey | Quantity | Unit | Unit Price | 92800 |  |  | 76005.2
| Labor | 1 | LS | 7300 | 7300 | 18% | 5975.2 | 5975.2
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 85500 | 85500 | 18% | 70030 | 70030
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
7 | Stabilized Construction Entrance | Quantity | Unit | Unit Price | 26400 |  |  | 21195.2
| Labor | 1 | LS | 11300 | 11300 | 18% | 9255.2 | 9255.2
| Materials | 1 | LS | 5800 | 5800 | 22% | 4500 | 4500
| Equipment | 1 | LS | 1500 | 1500 | 18% | 1200 | 1200
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 7400 | 7400 | 18% | 6000 | 6000
| Fuel | 1 | LS | 400 | 400 | 22% | 240 | 240
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
8 | Potholing and Utility Coordination | Quantity | Unit | Unit Price | 117000 |  |  | 95468
| Labor | 1 | LS | 75400 | 75400 | 18% | 61768 | 61768
| Materials | 1 | LS | 8400 | 8400 | 22% | 6500 | 6500
| Equipment | 1 | LS | 33200 | 33200 | 18% | 27200 | 27200
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
9 | Clearing and Grubbing | Quantity | Unit | Unit Price | 35100 |  |  | 28276.4
| Labor | 1 | LS | 18800 | 18800 | 18% | 15406.4 | 15406.4
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 7000 | 7000 | 18% | 5670 | 5670
| Fuel | 1 | LS | 9300 | 9300 | 22% | 7200 | 7200
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
10 | Site Restoration | Quantity | Unit | Unit Price | 35100 |  |  | 28276.4
| Labor | 1 | LS | 18800 | 18800 | 18% | 15406.4 | 15406.4
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 7000 | 7000 | 18% | 5670 | 5670
| Fuel | 1 | LS | 9300 | 9300 | 22% | 7200 | 7200
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
11 | As-Built Project Documents | Quantity | Unit | Unit Price | 26900 |  |  | 21975.2
| Labor | 1 | LS | 7300 | 7300 | 18% | 5975.2 | 5975.2
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 19600 | 19600 | 18% | 16000 | 16000
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
12 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
13 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
14 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
15 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
16 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
17 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
18 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
19 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
20 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
21 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
22 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
23 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
24 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
25 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
26 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
27 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
28 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
29 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
30 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
31 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
32 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
33 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
34 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
35 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0

## Bid Bond
| 0% | buffer for bid bond (dependent on confidence in all bid items)
Job Cost Breakdown | Totals
Labor | 202479.6
Equipment Rental | 44550
Subs | 115930
Material | 11000
Overhead | 35660
Profit | 197350.4
Other | 467240
Total Uncompleted Work | 1074210
| 1080000 | Estimate Project Total (for Bond, use a nice round number based on the "total uncompleted work" above)
| 10% | Bid Bond % (see specs)
| 3% | Performance Bond Premium %
| Bid Bond Check | 3.016%

## Bid Item 1
[8 empty] | Bid Item Total | 375000 | OUR COST
Mob/Demob - shall not exceed 5%
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 1 | VENDOR 2 | Total | COMMENT/NOTES
| Mobilization/Demobilization | [7 empty] | 375000
1 | Mobilization |  | 1 | ea | 325000 |  |  |  | 325000
2 | Demobilization |  | 1 | ea | 50000 |  |  |  | 50000
3 | [8 empty] | 0
Add More | [8 empty] | 0
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More | [8 empty] | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other (may sometimes include Bonds and Insurance) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 2
[8 empty] | Bid Item Total | 84694 | OUR COST
Environmental Compliance
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 30784
1 | Labor Lead |  | 40 | HR | 74.69 |  |  |  | 2987.6 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 120 | HR | 71.69 |  |  |  | 8602.8 | Assumes # of helpers to crew lead as outlined on "Bid Schedule" tab.
3 | Operator |  | 40 | HR | 96.29 |  |  |  | 3851.6
4 | Driver |  | 200 | HR | 76.71 |  |  |  | 15342
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 4800
1 | Mini Excavator |  | 80 | hr | 60 |  |  |  | 4800
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 9900
1 | SWPP |  | 1 | EA | 8500 | COAST |  |  | 8500
2 | SWPP Inspection & Reporting |  | 1 | EA | 1400 | COAST |  |  | 1400
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 27210
1 | Water Truck |  | 6 | month | 4535 |  |  |  | 27210 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 12000
1 | Diesel |  | 2000 | gal | 6 |  |  |  | 12000
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 3
[8 empty] | Bid Item Total | 43180.8 | OUR COST
Traffic Controls
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 23180.8
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 240 | HR | 71.69 |  |  |  | 17205.6 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 20000
1 | Traffic Control Plan |  | 1 | ea | 20000 |  |  |  | 20000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 4
[8 empty] | Bid Item Total | 23138 | OUR COST
Landowner Coordination
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 23138
1 | Labor Lead |  | 50 | HR | 74.69 |  |  |  | 3734.5 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 150 | HR | 71.69 |  |  |  | 10753.5 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 50 | HR | 96.29 |  |  |  | 4814.5
4 | Driver |  | 50 | HR | 76.71 |  |  |  | 3835.5
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0 | Hard hats, etc.
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 5
[8 empty] | Bid Item Total | 43990.4 | OUR COST
Develop and Provide Water Supply
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 11590.4
1 | Labor Lead |  | 40 | HR | 74.69 |  |  |  | 2987.6 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 120 | HR | 71.69 |  |  |  | 8602.8 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 14400
1 | Booster Pump |  | 6 | months | 1800 |  |  |  | 10800
2 | Mini Excavator |  | 60 | hr | 60 |  |  |  | 3600
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 18000
1 | Diesel |  | 3000 | gal | 6 |  |  |  | 18000
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0 | Month
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 6
[8 empty] | Bid Item Total | 76005.2 | OUR COST
Construction Survey
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 5975.2
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  |  | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 70030
1 | Construction Survey & Staking |  | 1 | EA | 70030 |  |  |  | 70030
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 7
[8 empty] | Bid Item Total | 21195.2 | OUR COST
Stabilized Construction Entrance
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 9255.2
1 | Labor Lead |  | 20 | HR | 74.69 |  |  |  | 1493.8 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 60 | HR | 71.69 |  |  |  | 4301.4 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 20 | HR | 96.29 |  |  |  | 1925.8
4 | Driver |  | 20 | HR | 76.71 |  |  |  | 1534.2
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 4500
1 | Rock |  | 1 | ea | 4500 |  |  |  | 4500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1200
1 | Mini Ex |  | 20 | hr | 60 |  |  |  | 1200
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 6000
1 | Rumble strips |  | 12 | months | 500 |  |  |  | 6000 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 240
1 | Diesel |  | 40 | gal | 6 |  |  |  | 240
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 8
[8 empty] | Bid Item Total | 95468 | OUR COST
Potholing and Utility Coordination
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 61768
1 | Labor Lead |  | 160 | HR | 74.69 |  |  |  | 11950.4 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 480 | HR | 71.69 |  |  |  | 34411.2 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 160 | HR | 96.29 |  |  |  | 15406.4
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 6500
1 | Misc Material |  | 1 | ea | 6500 |  |  |  | 6500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 27200
1 | Mini Ex |  | 160 | hr | 60 |  |  |  | 9600
2 | HydroVac |  | 4 | months | 4400 |  |  |  | 17600
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 9
[8 empty] | Bid Item Total | 28276.4 | OUR COST
Clearing and Grubbing
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 15406.4
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 160 | HR | 96.29 |  |  |  | 15406.4
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 5670
1 | Grader |  | 2 | weeks | 1600 |  |  |  | 3200 | For equipment rates see this spreadsheet:
2 | Skid Steer |  | 2 | Weeks | 1235 |  |  |  | 2470 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 7200
1 | Diesel |  | 1200 | gal | 6 |  |  |  | 7200
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 10
[8 empty] | Bid Item Total | 28276.4 | OUR COST
Site Restoration
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 15406.4
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 160 | HR | 96.29 |  |  |  | 15406.4
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 5670
1 | Grader |  | 2 | weeks | 1600 |  |  |  | 3200 | For equipment rates see this spreadsheet:
2 | Skid Steer |  | 2 | Weeks | 1235 |  |  |  | 2470 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 7200
1 | Diesel |  | 1200 | gal | 6 |  |  |  | 7200
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 11
[8 empty] | Bid Item Total | 21975.2 | OUR COST
As-Built Project Documents
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 5975.2
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  |  | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 16000
1 | As-Built |  | 1 | EA | 16000 |  |  |  | 16000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 12
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 13
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 14
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 15
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 16
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 17
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 18
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 19
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 20
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 21
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 22
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 23
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 24
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 25
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 26
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 27
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 28
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 29
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 30
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 31
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 32
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 33
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 34
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 35
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipe Fitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0