## Bid Summary
| Example 3C |  |  |  |  | 641850 |  | 708246 | Total bid Amount
UPDATE VALUES IN YELLOW |  |  | *Some agencies use a special code to identify the Bid Schedule
|  |  | Code* | Bid Schedule |  | Total with margin | Overhead | Total with overhead | QTY | Unit | Unit cost | Subtotals | Notes
| Notes |  | C-1 | 1 | Lateral DE Connection (18-inch Asbestos-Cement at STA 61+59.27) | 21991 | 5532.0833 | 27524 | 1 | LS | 27524 |  |  | 27524 | 27524
|  |  | C-1 | 2 | Lateral DE-C Connection (15-inch Asbestos-Cement at STA 61+13.24) | 28465 | 5532.0833 | 33998 | 1 | LS | 33998 |  |  | 33998 | 33998
Bid date: | 2025-05-30 |  | C-1 | 3 | Removal and Disposal of Existing Laterals (Lat DE Steel Pipe on C-303) | 18001 | 5532.0833 | 23534 | 1 | LS | 23534 |  |  | 23534 | 23534
Award date: | 2025-06-15 |  | C-1 | 4 | Removal and Disposal of Existing Laterals and Turnout Connections (Asbestos-Cement Pipe on C-303) | 22489 | 5532.0833 | 28022 | 1 |  | 28022 |  |  | 28022 | 28022
Notice date: | 2025-07-15 |  | C-1 | 5 | Removal and Disposal of Existing Marker Posts and Cathodic Protection Test Stations | 6349 | 5532.0833 | 11882 | 1 |  | 11882 |  |  | 11882 | 11882
Start Date: | 2025-07-17 |  | C-1 | 6 | 24-inch PVC Pipe (Lateral DE) | 344197 | 9532.0833 | 353730 | 2616 |  | 135.2179 |  |  | 136 | 355776
Complete by: | 2026-01-31 |  | C-1 | 7 | Removal and Reconnection of Turnout 22D (10-inch Asbestos-Cement at STA 60+88.4) | 49904 | 5532.0833 | 55437 | 1 |  | 55437 |  |  | 55437 | 55437
|  |  | C-1 | 8 | 10-inch Buried Service Butterfly Valve Assembly | 13644 | 5532.0833 | 19177 | 1 |  | 19177 |  |  | 19177 | 19177
Work Days: | 198 | (including weekends) | C-1 | 9 | 14-inch Buried Service Butterfly Valve Assembly | 16657 | 5532.0833 | 22190 | 1 |  | 22190 |  |  | 22190 | 22190
|  |  | C-1 | 10 | 2-inch Underground Combination Air Valve Assembly | 67868 | 5532.0833 | 73401 | 2 |  | 36700.5 |  |  | 36701 | 73402
|  |  | C-1 | 11 | Color Coded Marker Posts | 10354 | 1532.0833 | 11887 | 4 |  | 2971.75 |  |  | 2972 | 11888
| 1000 | Liquidated Damages ($/day) | C-1 | 12 | Hydrostatic Pressure Testing (24-inch Lateral DE and Connections) | 41931 | 5532.0833 | 47464 | 1 |  | 47464 |  |  | 47464 | 47464
|  |  | C-1 | 13 |  | 0 | 0 | 0 | 1 |  | 0 |  |  |  | 710294
|  |  | C-1 | 14 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 15 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 16 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 17 |  | 0 | 0 | 0 | 1 |  | 0
| 66385 | Project Overhead to be dispersed | C-1 | 18 |  | 0 | 0 | 0 | 1 |  | 0
| 12 | Number of Bid Items to spread overhead | C-1 | 19 |  | 0 | 0 | 0 | 1 |  | 0
| 5532.0833 | Overhead $$ / site | C-1 | 20 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 21 |  | 0 | 0 | 0 | 1 |  | 0
| 9.373% | Overhead as a % of Total | C-1 | 22 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 23 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 24 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 25 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 26 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 27 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 28 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 29 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 30 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 31 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 32 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 33 |  | 0 | 0 | 0 | 1 |  | 0
|  |  | C-1 | 34 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 35 |  | 0 | 0 | 0 | 1 |  | 0
[7 empty] | 66385 | (check against Cell B21)

## Prevailing Wage
Step #1
Review the Plan Set and the Specifications to identify the type of work that will be done.
Step #2
Use this link to identify potential wage determinations for those jobs:
*Ensure you are in the correct county.
https://www.dir.ca.gov/oprl/2024-1/PWD/Determinations/Subtrades/jrnylist.html
Step #3
List the Classification as well as the corresponding wage determinations:
| Classification | Wage ($/hr) | Jobs/Tasks | Justification | Task Code (if used)
1 | Labor Lead | 74.69
2 | Laborer | 71.69
3 | Operator | 96.29
4 | Driver | 76.71
5 | Landscaper
6 | Plumber | 87.69
7 | Etc
8 | Etc
*For justification, see "Scope of Work Provisions" link in the wage determinations from the link above.
*Wage is non-overtime.

## Bid Schedule
Example 3C | [10 empty] | Crew Info
[11 empty] | 3 | multiplier (helpers to leadman)
[11 empty] | 8 | working hours per day
Bid # | Description | Quantity | Unit | Unit Price | Total | MARGIN | OUR COST | TOTAL COST | RESPONSIBLE PARTY |  |  |  | Category | Our Cost | Sale Price
[13 empty] | Overhead | 51869.59 | 63420
| Project OVERHEAD | Quantity | Unit | Unit Price | 63420 | 18.21% |  | 51869.59 | LAW | Margin |  |  | Mob/Demob | 0 | 0
| Bonding | 1 | EA | 26550 | 26550 | 18% | 21769.59 | 21769.59 | LAW | 18% | In-house |  | Labor | 156734.72 | 191146
| Insurance | 1 | EA | 2440 | 2440 | 18% | 2000 | 2000 | LAW | 22% | Material |  | Materials | 275627.79 | 353374
| Restrooms | 4 | Months | 1465 | 5860 | 18% | 1200 | 4800 | LAW | 18% | Subs |  | Equipment | 12640 | 15419
| Administrative | 40 | HR | 122 | 4880 | 18% | 100 | 4000 | LAW | 18% | Equipment |  | Subs | 0 | 0
| Project Management | 200 | HR | 86 | 17200 | 18% | 70 | 14000 | LAW | 18% | Other |  | Rental | 33683.7 | 41082
| Permitting/Submittal Support | 40 | HR | 86 | 3440 | 18% | 70 | 2800 | LAW |  |  |  | Fuel | 26040 | 33389
| PM Fuel | 1 | LS | 3050 | 3050 | 18% | 2500 | 2500 | LAW |  |  |  | Other | 6100 | 7440
| Travel/Hotels | 1 | Days | 0 | 0 | 18% | 0 | 0 | LAW
| Per Diem | 1 | Days | 0 | 0 | 18% | 0 | 0 | LAW |  |  |  | Subtotal | 562695.8 | 705270
[14 empty] | 20.55% | Margin (back-calculated)
BID SCHEDULE ITEMS
1 | Lateral DE Connection (18-inch Asbestos-Cement at STA 61+59.27) | Quantity | Unit | Unit Price | 21991 |  | Our Cost | 17617.31 | [6 empty] | 142574.2
| Mobilization/Demobilization | 1 | EA | 0 | 0 | 18% | 0 | 0 |  | Labor Hrs | Labor days |  | Crew days | Crew weeks
| Labor | 1 | LS | 9030 | 9030 | 18% | 7404.16 | 7404.16 |  | 2032 | 254 |  | 63.5 | 12.7
| Materials | 1 | LS | 8473 | 8473 | 22% | 6608.3 | 6608.3
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1970 | 1970 | 18% | 1614.85 | 1614.85
| Fuel | 1 | LS | 1847 | 1847 | 22% | 1440 | 1440
| Other | 1 | LS | 671 | 671 | 18% | 550 | 550
Blank
2 | Lateral DE-C Connection (15-inch Asbestos-Cement at STA 61+13.24) | Quantity | Unit | Unit Price | 28465 |  |  | 22667.56
| Labor | 1 | LS | 9030 | 9030 | 18% | 7404.16 | 7404.16
| Materials | 1 | LS | 14947 | 14947 | 22% | 11658.55 | 11658.55
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1970 | 1970 | 18% | 1614.85 | 1614.85
| Fuel | 1 | LS | 1847 | 1847 | 22% | 1440 | 1440
| Other | 1 | LS | 671 | 671 | 18% | 550 | 550
3 | Removal and Disposal of Existing Laterals (Lat DE Steel Pipe on C-303) | Quantity | Unit | Unit Price | 18001 |  |  | 14666.91
| Labor | 1 | LS | 9030 | 9030 | 18% | 7404.16 | 7404.16
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 3614 | 3614 | 18% | 2962.75 | 2962.75
| Fuel | 1 | LS | 2308 | 2308 | 22% | 1800 | 1800
| Other | 1 | LS | 3049 | 3049 | 18% | 2500 | 2500
4 | Removal and Disposal of Existing Laterals and Turnout Connections (Asbestos-Cement Pipe on C-303) | Quantity | Unit | Unit Price | 22489 |  |  | 18166.91
| Labor | 1 | LS | 9030 | 9030 | 18% | 7404.16 | 7404.16
| Materials | 1 | LS | 4488 | 4488 | 22% | 3500 | 3500
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 3614 | 3614 | 18% | 2962.75 | 2962.75
| Fuel | 1 | LS | 2308 | 2308 | 22% | 1800 | 1800
| Other | 1 | LS | 3049 | 3049 | 18% | 2500 | 2500
5 | Removal and Disposal of Existing Marker Posts and Cathodic Protection Test Stations | Quantity | Unit | Unit Price | 6349 |  |  | 5202.08
| Labor | 1 | LS | 4515 | 4515 | 18% | 3702.08 | 3702.08
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 1757 | 1757 | 18% | 1440 | 1440
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 77 | 77 | 22% | 60 | 60
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
6 | 24-inch PVC Pipe (Lateral DE) | Quantity | Unit | Unit Price | 344197 |  |  | 271444.44
| Labor | 1 | LS | 54542 | 54542 | 18% | 44724 | 44724
| Materials | 1 | LS | 254520 | 254520 | 22% | 198525.44 | 198525.44
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 19750 | 19750 | 18% | 16195 | 16195
| Fuel | 1 | LS | 15385 | 15385 | 22% | 12000 | 12000
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
7 | Removal and Reconnection of Turnout 22D (10-inch Asbestos-Cement at STA 60+88.4) | Quantity | Unit | Unit Price | 49904 |  |  | 40372.4
| Labor | 1 | LS | 22574 | 22574 | 18% | 18510.4 | 18510.4
| Materials | 1 | LS | 12131 | 12131 | 22% | 9462 | 9462
| Equipment | 1 | LS | 8781 | 8781 | 18% | 7200 | 7200
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 4879 | 4879 | 18% | 4000 | 4000
| Fuel | 1 | LS | 1539 | 1539 | 22% | 1200 | 1200
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
8 | 10-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 13644 |  |  | 10891.58
| Labor | 1 | LS | 4515 | 4515 | 18% | 3702.08 | 3702.08
| Materials | 1 | LS | 7372 | 7372 | 22% | 5749.5 | 5749.5
| Equipment | 1 | LS | 1757 | 1757 | 18% | 1440 | 1440
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
9 | 14-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 16657 |  |  | 13242.08
| Labor | 1 | LS | 4515 | 4515 | 18% | 3702.08 | 3702.08
| Materials | 1 | LS | 10385 | 10385 | 22% | 8100 | 8100
| Equipment | 1 | LS | 1757 | 1757 | 18% | 1440 | 1440
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
10 | 2-inch Underground Combination Air Valve Assembly | Quantity | Unit | Unit Price | 67868 |  |  | 54016.44
| Labor | 1 | LS | 24844 | 24844 | 18% | 20371.44 | 20371.44
| Materials | 1 | LS | 35288 | 35288 | 22% | 27524 | 27524
| Equipment | 1 | LS | 781 | 781 | 18% | 640 | 640
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1416 | 1416 | 18% | 1161 | 1161
| Fuel | 1 | LS | 5539 | 5539 | 22% | 4320 | 4320
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
11 | Color Coded Marker Posts | Quantity | Unit | Unit Price | 10354 |  |  | 8248.4
| Labor | 1 | LS | 3767 | 3767 | 18% | 3088.4 | 3088.4
| Materials | 1 | LS | 5770 | 5770 | 22% | 4500 | 4500
| Equipment | 1 | LS | 586 | 586 | 18% | 480 | 480
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 231 | 231 | 22% | 180 | 180
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
12 | Hydrostatic Pressure Testing (24-inch Lateral DE and Connections) | Quantity | Unit | Unit Price | 41931 |  |  | 34290.1
| Labor | 1 | LS | 35754 | 35754 | 18% | 29317.6 | 29317.6
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 3869 | 3869 | 18% | 3172.5 | 3172.5
| Fuel | 1 | LS | 2308 | 2308 | 22% | 1800 | 1800
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
13 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
14 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
15 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
16 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
17 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
18 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
19 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
20 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
21 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
22 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
23 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
24 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
25 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
26 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
27 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
28 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
29 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
30 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
31 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
32 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
33 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
34 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
35 | 0 | Quantity | Unit | Unit Price | 0 |  |  | 0
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 22% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 22% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0

## Bid Bond
| 30% | buffer for bid bond (dependent on confidence in all bid items)
Job Cost Breakdown | Totals
Labor | 203755.136
Equipment Rental | 43788.81
Subs | 0
Material | 358316.127
Overhead | 67430.467
Profit | 185346.46
Other | 58214
Total Uncompleted Work | 916851
| 725653 | Estimate Project Total (for Bond, use a nice round number based on the "total uncompleted work" above)
| 10% | Bid Bond % (see specs)
| 3% | Performance Bond Premium %
| Bid Bond Check | 3.074%

## Bid Item 1
[8 empty] | Bid Item Total | 17617.31 | OUR COST
Lateral DE Connection (18-inch Asbestos-Cement at STA 61+59.27)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 1 | VENDOR 2 | Total | COMMENT/NOTES
| Mobilization/Demobilization | [7 empty] | 0
1 | Mobilization | [7 empty] | 0
2 | Demobilization | [7 empty] | 0
3 | [8 empty] | 0
Add More | [8 empty] | 0
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More | [8 empty] | 0
| Materials | [7 empty] | 6608.3
1 | 18" PVC TO AC PIPE COUPLING |  | 1 |  | 2854.75 |  |  |  | 2854.75
2 | 18" RFCA |  | 1 | ea | 2854.75 | PACE |  |  | 2854.75 | RMCRFCA1950 RFCA 19.50 RESTRAINED FLG CPLG ADA ROMAC
3 | 18" PVC Pipe |  | 20 | ft | 44.94 | JM |  |  | 898.8
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1614.85
1 | 85K Excavator |  | 0.15 | Month | 6054 |  |  |  | 908.1 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.45 | Month | 605 |  |  |  | 272.25
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other (may sometimes include Bonds and Insurance) | [7 empty] | 550
1 | Temporary Fittings |  | 1 | EA | 550 |  |  |  | 550
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 2
[8 empty] | Bid Item Total | 22667.56 | OUR COST
Lateral DE-C Connection (15-inch Asbestos-Cement at STA 61+13.24)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on "Bid Schedule" tab.
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 11658.55
1 | 24"x24"x14" TEE RT |  | 1 |  | 8000 |  |  |  | 8000
2 | 14" RFCA |  | 1 |  | 1891.25 | PACE |  |  | 1891.25 | NS00184518 14" ROMAC RFCA 15.30 OD SHOP COAT 304SS
3 | 14" PVC Pipe |  | 40 |  | 27.72 |  |  |  | 1108.8
4 | 14" MJ Coup PVC X AC |  | 1 | ea | 658.5 | PACE |  |  | 658.5 | NS00256323 HYMAX CLAMP 14"(14.20-15.80)12" Length 150 PSI
0
0
0
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1614.85
1 | 85K Excavator |  | 0.15 | Month | 6054 |  |  |  | 908.1 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.45 | Month | 605 |  |  |  | 272.25
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 550
1 | Temporary Fittings |  | 1 | EA | 550 |  |  |  | 550
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 3
[8 empty] | Bid Item Total | 14666.91 | OUR COST
Removal and Disposal of Existing Laterals (Lat DE Steel Pipe on C-303)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 2962.75
1 | 85K Excavator |  | 0.25 | Month | 6054 |  |  |  | 1513.5 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.25 | Month | 4345 |  |  |  | 1086.25 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.6 | Month | 605 |  |  |  | 363
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1800
1 | Diesel |  | 300 | Gal | 6 |  |  |  | 1800
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 2500
1 | Disposal Fee |  | 1 | TRKs | 2500 |  |  |  | 2500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 4
[8 empty] | Bid Item Total | 18166.91 | OUR COST
Removal and Disposal of Existing Laterals and Turnout Connections (Asbestos-Cement Pipe on C-303)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 3500
1 | 18" CONC PIPE | MATERIAL TO REMOVE | 20 | LF |  |  |  |  | 0
2 | 18" ACP CL40 | MATERIAL TO REMOVE | 50 | LF |  |  |  |  | 0
3 | INSTALL PLUG 18" (concrete & sandbags) |  | 1 | LS |  |  |  |  | 0
4 | 15" ACP CL35 | MATERIAL TO REMOVE | 8 | LF |  |  |  |  | 0
5 | Misc Fitttings |  | 1 | ea | 3500 |  |  |  | 3500
6 | [8 empty] | 0
7 | [8 empty] | 0
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 2962.75
1 | 85K Excavator |  | 0.25 | Month | 6054 |  |  |  | 1513.5 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.25 | Month | 4345 |  |  |  | 1086.25 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.6 | Month | 605 |  |  |  | 363
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1800
1 | Diesel |  | 300 | gal | 6 |  |  |  | 1800
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 2500
1 | Disposal Fee |  | 1 | TRKs | 2500 |  |  |  | 2500 | Hard hats, etc.
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 5
[8 empty] | Bid Item Total | 5202.08 | OUR COST
Removal and Disposal of Existing Marker Posts and Cathodic Protection Test Stations
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3702.08
1 | Labor Lead |  | 8 | HR | 74.69 |  |  |  | 597.52 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 71.69 |  |  |  | 1720.56 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 96.29 |  |  |  | 770.32
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | marker post | item to remove | 1 | [5 empty] | 0
2 | cp test station | item to remove | 1 | [5 empty] | 0
3 | gate post | item to remove | 1 | [5 empty] | 0
4 | [8 empty] | 0
0
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1440
1 | Mini Excavtor |  | 8 | hr | 60 |  |  |  | 480
2 | Trucking |  | 8 | hr | 120 |  |  |  | 960
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 60
1 | Diesel |  | 10 | gal | 6 |  |  |  | 60
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0 | Month
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 6
[8 empty] | Bid Item Total | 271444.44 | OUR COST
24-inch PVC Pipe (Lateral DE)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 44724
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 240 | HR | 71.69 |  |  |  | 17205.6 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 160 | HR | 96.29 |  |  |  | 15406.4
4 | Driver |  | 80 | HR | 76.71 |  |  |  | 6136.8
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0 |  |  | 72919
Add More |  |  |  | HR |  |  |  |  | 0 |  |  | 27.8742
| Materials | [7 empty] | 198525.44
1 | 24-inch PVC Pipe C900 DR 25 |  | 2616 | LF | 70.59 |  |  |  | 184663.44 |  | 8.72
2 | 24" 45* Elbow Hymax (OR DI ELBOW?) |  | 2 |  | 1960.5 | PACE |  |  | 3921 | DCF45MJ24 24 MJ 45 ELL AC CL | 72
3 | Concrete for Thrust Blocks |  | 2 |  | 1000 |  |  |  | 2000
4 | 24" X 18" RED COUP |  | 1 |  | 2000 |  |  |  | 2000 | 24*16 DI FLG CONC REDUCER BLK $1947.55 - pace 03/2025
| 24" BELL RESTRAINT 1100C PVC C900 |  | 4 | ea | 1485.25 | PACE |  |  | 5941 | NS00186465 24 BELL RESTRAINER C900/DI
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 16195
1 | 120K Excavator |  | 0.5 | Month | 13100 |  |  |  | 6550 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.5 | Month | 6055 |  |  |  | 3027.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.5 | Month | 4345 |  |  |  | 2172.5
4 | Compaction |  | 2 | Month | 605 |  |  |  | 1210
| Shoring |  | 0 | Months | 35000 |  |  |  | 0
| Telehandler |  | 1 | Month | 3235 |  |  |  | 3235
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 12000
1 | Diesel |  | 2000 | gal | 6 |  |  |  | 12000
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 7
[8 empty] | Bid Item Total | 40372.4 | OUR COST
Removal and Reconnection of Turnout 22D (10-inch Asbestos-Cement at STA 60+88.4)
| ITEM | BID PACKET PAGE | QTY | UNIT | t | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 18510.4
1 | Labor Lead |  | 40 | HR | 74.69 |  |  |  | 2987.6 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 120 | HR | 71.69 |  |  |  | 8602.8 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 40 | HR | 96.29 |  |  |  | 3851.6 |  | Removal and Reconnection of Turnout 22D (10-inch Asbestos-Cement at STA 60+88.4)
4 | Driver |  | 40 | HR | 76.71 |  |  |  | 3068.4
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 9462
1 | 10" ACP CL35 PIPE | PG. 28_MATERIAL TO REMOVE | 2 | LF |  |  |  |  | 0
2 | 24"x24"x10" TEE OR OUTLET 10" BFV (N) | PG. 28_MATERIAL TO REMOVE | 1 | EA |  |  |  |  | 0
3 | 10" PVC C900 DR 25 PIPE | PG. 47_QTY NOT SPECIFIED | 20 | LF | 18.8 |  |  |  | 376
4 | 10" C900 X STL COUP | PG. 47 | 1 | EA | 670 |  |  |  | 670 | HYM2CPLG10 10 CPLG 10.70-12.00 OD 860-54-0272-16 HYMAX2
5 | 10" CARBON STEEL PIPE .25" | PG. 47 | [6 empty] | 0
6 | 10" CARBON STEEL ELBOW .25" | PG. 47 | 1 | [5 empty] | 0
7 | 10" CLASS D FLG | PG. 47 | 1 |  | 35 |  |  |  | 35 | 150 CLASS LIGHT IRRIG SLIP FLG
8 | CRUSHED ROCK 3/4" | PG. 47 | 1 | CY |  |  |  |  | 0
9 | CO JOINT 48" X 24" CLIII | PG. 47 | 1 | [5 empty] | 0
10 | SWSD METER, VALVE, LANDOWNER PIPING | PG. 47_TO BE REINSTALLED | [6 empty] | 0
11 | 10" FLG Adap MJ |  | 1 | ea | 381 |  |  |  | 381
12 | 24" x 24" x 10" MJ X FLG Tee |  | 1 | ea | 6000 |  |  |  | 6000
13 | Concrete |  | 1 | ea | 2000 |  |  |  | 2000
14 | [8 empty] | 0
15 | [8 empty] | 0
16 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 7200
1 | Mini Excavtor |  | 40 | hr | 60 |  |  |  | 2400
2 | Trucking |  | 40 | hr | 120 |  |  |  | 4800
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 4000
1 | Compaction |  | 1 | ea | 4000 |  |  |  | 4000 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1200
1 | Diesel |  | 200 | gal | 6 |  |  |  | 1200
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 8
[8 empty] | Bid Item Total | 10891.58 | OUR COST
10-inch Buried Service Butterfly Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3702.08
1 | Labor Lead |  | 8 | HR | 74.69 |  |  |  | 597.52 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 71.69 |  |  |  | 1720.56 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 96.29 |  |  |  | 770.32
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 5749.5
1 | 10" BFV Valmatic |  | 1 | ea | 2892 |  |  |  | 2892 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
2 | Bolt kit 10" FxF SS |  | 2 | ea | 200 |  |  |  | 400
| 10" Blind Flange |  | 1 | ea | 62.5 | BPS |  |  | 62.5 | 150 CLASS LIGHT IRRIG BLIND FLG
| Coating |  | 1 | ea | 1000 |  |  |  | 1000
| Concrete |  | 1 | ea | 1000 |  |  |  | 1000
| PVC 8" SDR 35 |  | 20 | ea | 18 |  |  |  | 360 | PVC SLEEVE FOR STEM
| 10" FLANGE |  | 1 | ea | 35 | BPS |  |  | 35 | 150 CLASS LIGHT IRRIG SLIP FLG
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1440
1 | Mini Excavtor |  | 8 | hr | 60 |  |  |  | 480
2 | Trucking |  | 8 | hr | 120 |  |  |  | 960
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 9
[8 empty] | Bid Item Total | 13242.08 | OUR COST
14-inch Buried Service Butterfly Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3702.08
1 | Labor Lead |  | 8 | HR | 74.69 |  |  |  | 597.52 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 71.69 |  |  |  | 1720.56 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 96.29 |  |  |  | 770.32
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 8100
1 | 14" BFV Valmatic |  | 1 | ea | 4954 |  |  |  | 4954 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
2 | Bolt kit 14" FxF SS |  | 2 | ea | 300 |  |  |  | 600
| 14" Blind Flange |  | 1 | ea | 121 |  |  |  | 121 | 150 CLASS LIGHT IRRIG BLIND FLG
| Coating |  | 1 | ea | 1000 |  |  |  | 1000
| Concrete |  | 1 | ea | 1000 |  |  |  | 1000
| PVC 8" SDR 35 |  | 20 | ea | 18 |  |  |  | 360
| 14" FLANGE |  | 1 | ea | 65 |  |  |  | 65 | 150 CLASS LIGHT IRRIG SLIP FLG
0
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1440
1 | Mini Excavtor |  | 8 | hr | 60 |  |  |  | 480
2 | Trucking |  | 8 | hr | 120 |  |  |  | 960
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 10
[8 empty] | Bid Item Total | 54016.44 | OUR COST
2-inch Underground Combination Air Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 20371.44
1 | Labor Lead |  | 48 | HR | 74.69 |  |  |  | 3585.12 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 144 | HR | 71.69 |  |  |  | 10323.36 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 48 | HR | 96.29 |  |  |  | 4621.92
4 | Driver |  | 24 | HR | 76.71 |  |  |  | 1841.04
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 27524
1 | 24" Tapping Sleeve with 2" threaded outlet |  | 2 | ea | 4000 |  |  |  | 8000
2 | 2" Galv S40 Welded Steel Pipe Nipple Long TBE |  | 2 | ea | 20 |  |  |  | 40
3 | 2" Gate Valve, Stockham Fig 120 |  | 2 | ea | 200 |  |  |  | 400
4 | 2" Galv S40 Welded Steel Pipe Nipple Short TBE |  | 2 | ea | 15 |  |  |  | 30
| 2" Val-Matic Series 201CSSA |  | 2 | ea | 1407 |  |  |  | 2814 | Val-Matic Combination Air Release Valve for Water, Cast Iron Body, 316 Stainless Steel Trim & Float, Threaded Screen Hood, Buna-N Seat, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 300 PSI CWP. ***IF regulated exhaust is requred Please add $377.00 Each.***.
| 2" Galv Sch 40 90* Street |  | 2 | ea | 20 |  |  |  | 40
| 2" Prefabricated fittings with integral ss screen |  | 2 | ea | 100 |  |  |  | 200
| Concrete Box with manhole - traffic rated - Page 40 in plans |  | 2 | ea | 8000 |  |  |  | 16000
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 640
1 | Mini Ex |  | 8 | HR | 80 |  |  |  | 640
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1161
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.1 | Month | 6055 |  |  |  | 605.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
Add More | Telehandler |  | 0 | Month | 3235 |  |  |  | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 4320
1 | Diesel |  | 720 | Gal | 6 |  |  |  | 4320
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 11
[8 empty] | Bid Item Total | 8248.4 | OUR COST
Color Coded Marker Posts
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3088.4
1 | Labor Lead |  | 8 | HR | 74.69 |  |  |  | 597.52 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 71.69 |  |  |  | 1720.56 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 96.29 |  |  |  | 770.32
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 4500
1 | marker post - red (buried Valve) |  | 2 | [5 empty] | 0
2 | marker post - blue (air valve) |  | 1 | [5 empty] | 0
3 | 4" Steel Pipe S40 |  | 100 | ft | 15 |  |  |  | 1500
4 | Concrete |  | 1 | ea | 3000 |  |  |  | 3000
0
0
0
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 480
1 | mini Excavator |  | 8 | HR | 60 |  |  |  | 480
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 180
1 | Diesel |  | 30 | gal | 6 |  |  |  | 180
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 12
[8 empty] | Bid Item Total | 34290.1 | OUR COST
Hydrostatic Pressure Testing (24-inch Lateral DE and Connections)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 29317.6
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 240 | HR | 71.69 |  |  |  | 17205.6 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  | 80 | HR | 76.71 |  |  |  | 6136.8
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
0
0
0
0
0
0
0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 3172.5
1 | Water Truck |  | 0.5 | Month | 4345 |  |  |  | 2172.5 | For equipment rates see this spreadsheet:
2 | Pump |  | 2 | weeks | 500 |  |  |  | 1000 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1800
1 | Diesel |  | 300 | gal | 6 |  |  |  | 1800
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 13
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 14
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 15
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 16
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 17
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 18
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 19
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 20
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 21
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 22
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 23
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 24
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 25
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 26
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 27
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 28
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 29
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 30
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 31
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 32
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 33
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 34
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 35
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Plumber |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0