## Base Bid Summary
| Average PW Job - Example 6 |  |  |  |  | 473173.76 |  | 541871 | Total bid Amount w/ Sales Tax
Legend: |  |  | *Some agencies use a special code to identify the Bid Schedule |  |  |  |  | Eng. Est: 480,000 |  |  |  | 565522 |  | 452417.6
Input values |  |  | Code* | Bid Schedule |  | Total with margin | Overhead | Total with overhead | QTY | Unit | Unit cost | Subtotals | Notes
Default values you can adjust |  |  |  | 1 | Mob/Demob | 51396 | 4906.4743 | 56303 | 1 | LS | 56303
Calculated input values |  |  |  | 2 | Site Demo | 38068 | 4906.4743 | 42975 | 1 | LS | 42975
Cost totals |  |  |  | 3 | Clearing, Grubbing, Stripping & Tree Removal | 18736.25 | 4906.4743 | 23643 | 1 | LS | 23643
Totals with margin and taxes |  |  |  | 4 | Temporary Dewatering | 59578.75 | 4906.4743 | 64486 | 1 | LS | 64486
|  |  |  | 5 | SWPPP Compliance | 30587.8225 | 4906.4743 | 35495 | 1 | LS | 35495
|  |  |  | 6 | Coanda Screen | 8663.375 | 4906.4743 | 13570 | 1 | LS | 13570
Dates: |  |  |  | 7 | Weir Bypass | 7680.01 | 4906.4743 | 12587 | 1 | LS | 12587
Bid date: | 2025-07-08 |  |  | 8 | 6-inch C900 PVC Pipe | 12421.9625 | 4906.4743 | 17329 | 15 | LF | 1155.2667
Award date: | 2025-07-18 |  |  | 9 | Earthwork | 53650 | 4906.4743 | 58557 | 150 | CY | 390.38
NTP date: | 2025-08-17 |  |  | 10 | Rock Slope Protection | 44146 | 4906.4743 | 49053 | 20 | CY | 2452.65
Start Date: | 2025-08-17 | within 30 days of contract execution |  | 11 | Native Rock | 22740 | 4906.4743 | 27647 | 20 | CY | 1382.35
Complete by: | 2025-10-31 |  |  | 12 | Cast-in-Place Concrete | 110948 | 4906.4743 | 115855 | 50 | CY | 2317.1
|  |  |  | 13 | Staff Gauge | 4966.3125 | 4906.4743 | 9873 | 1 | EA | 9873
Work Days: | 75 | (including weekends) |  | 14 | 6-inch Gate Valve | 9591.2775 | 4906.4743 | 14498 | 1 | EA | 14498
|  |  | A1.1 | 15 | Temporary Dewatering
|  |  | A1.2 | 16 | Demo pipe
| 1000 | Liquidated Damages ($/day) prior to substantial completion | A1.3 | 17 | 6-inch PVC pipe
| 500 | Liquidated Damages ($/day) prior to final compl | A1.4 | 18 | Hard Rock Excavation
|  |  | A2.1 | 19 | Stilling well
|  |  | A2.2 | 20 | Solar Mast
|  |  | A2.3 | 21 | Level Transducer
|  |  |  | 22 |  | 0 | 0 | 0 | 1 |  | 0
| 68690.64 | Project Overhead to be dispersed |  | 23 |  | 0 | 0 | 0 | 1 |  | 0
| 14 | Number of Bid Items (to spread overhead) |  | 24 |  | 0 | 0 | 0 | 1 |  | 0
| 4906.4743 | Overhead $$ / site |  | 25 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 26 |  | 0 | 0 | 0 | 1 |  | 0
| 9.651% | Overhead as a % of Total |  | 27 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 28 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 29 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 30 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 31 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 32 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 33 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 34 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 35 |  | 0 | 0 | 0 | 1 |  | 0
[7 empty] | 68690.64 | (check against Cell B21)

## Alt Bid Summary
| Alternate Bids |  |  |  |  | 178874.8675 |  | 213224 | Total bid Amount w/ Sales Tax
Legend: |  |  | *Some agencies use a special code to identify the Bid Schedule |  |  |  |  | Eng. Est: 480,000
Input values |  |  | Code* | Bid Schedule |  | Total with margin | Overhead | Total with overhead | QTY | Unit | Unit cost | Subtotals | Notes
Default values you can adjust |  |  |  | 1 | Mob/Demob
Calculated input values |  |  |  | 2 | Site Demo
Cost totals |  |  |  | 3 | Clearing, Grubbing, Stripping & Tree Removal
Totals with margin and taxes |  |  |  | 4 | Temporary Dewatering
|  |  |  | 5 | SWPPP Compliance
|  |  |  | 6 | Coanda Screen
Dates: |  |  |  | 7 | Weir Bypass
Bid date: | 2025-07-08 |  |  | 8 | 6-inch C900 PVC Pipe
Award date: | 2025-07-18 |  |  | 9 | Earthwork
NTP date: | 2025-08-17 |  |  | 10 | Rock Slope Protection
Start Date: | 2025-08-17 | within 30 days of contract execution |  | 11 | Native Rock
Complete by: | 2025-10-31 |  |  | 12 | Cast-in-Place Concrete
|  |  |  | 13 | Staff Gauge
Work Days: | 75 | (including weekends) |  | 14 | 6-inch Gate Valve
|  |  | A1.1 | 15 | Temporary Dewatering | 88704.75 | 4906.4743 | 93612 | 1 | LS | 93612
|  |  | A1.2 | 16 | Demo pipe | 17050.1975 | 4906.4743 | 21957 | 57 | LF | 385.2105
| 1000 | Liquidated Damages ($/day) prior to substantial completion | A1.3 | 17 | 6-inch PVC pipe | 9779.25 | 4906.4743 | 14686 | 57 | LF | 257.6491
| 500 | Liquidated Damages ($/day) prior to final compl | A1.4 | 18 | Hard Rock Excavation | 18744.01 | 4906.4743 | 23651 | 10 | CY | 2365.1
|  |  | A2.1 | 19 | Stilling well | 7251 | 4906.4743 | 12158 | 1 | LS | 12158
|  |  | A2.2 | 20 | Solar Mast | 27771.01 | 4906.4743 | 32678 | 1 | LS | 32678
|  |  | A2.3 | 21 | Level Transducer | 9574.65 | 4906.4743 | 14482 | 1 | LS | 14482
|  |  |  | 22 |  | 0 | 0 | 0 | 1 |  | 0
| 68690.64 | Project Overhead to be dispersed |  | 23 |  | 0 | 0 | 0 | 1 |  | 0
| 14 | Number of Bid Items (to spread overhead) |  | 24 |  | 0 | 0 | 0 | 1 |  | 0
| 4906.4743 | Overhead $$ / site |  | 25 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 26 |  | 0 | 0 | 0 | 1 |  | 0
| 9.651% | Overhead as a % of Total |  | 27 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 28 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 29 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 30 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 31 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 32 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 33 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 34 |  | 0 | 0 | 0 | 1 |  | 0
|  |  |  | 35 |  | 0 | 0 | 0 | 1 |  | 0
[7 empty] | 34345.32 | (check against Cell B21)

## Prevailing Wage
Step #1
Review the Plan Set and the Specifications to identify the type of work that will be done.
Step #2
Use this link to identify potential wage determinations for those jobs:
*Ensure you are in the correct county.
https://www.dir.ca.gov/oprl/2024-1/PWD/Determinations/Subtrades/jrnylist.html
Step #3
List the Classification as well as the corresponding wage determinations:
| Classification | Wage ($/hr) | Group/Classification | Description/Tasks | Task Code (if used) | DIR Link
1 | Labor Lead | 67.36 | Area 2; Constr Specialist |  |  | https://www.dir.ca.gov/oprl/2025-1/PWD/Determinations/Northern/NC-023-102-1.pdf
2 | Laborer | 66.41 | Area 2; Group 3 |  |  | https://www.dir.ca.gov/oprl/2025-1/PWD/Determinations/Northern/NC-023-102-1.pdf
3 | Operator | 94.64 | Area 1; Group 3 |  |  | https://www.dir.ca.gov/oprl/2025-1/PWD/Determinations/Northern/NC-023-63-1.pdf
4 | Electrician | 89.3 | Comm & System Installer |  |  | https://www.dir.ca.gov/oprl/2024-1/PWD/Determinations/Subtrades/YUB.html
5 | Pipe Fitter | 68.79 | Underground utility pipefitter |  |  | https://www.dir.ca.gov/oprl/2024-1/PWD/Determinations/Subtrades/YUB.html
6 | Truck Driver | 76.87 | Trucks (Any) |  |  | https://www.dir.ca.gov/oprl/2025-1/PWD/Determinations/Northern/NC-023-261-1.pdf
7 | Landscaper
8 | Etc
*For justification, see "Scope of Work Provisions" link in the wage determinations from the link above.
| *Wage is non-overtime. |  |  |  |  | https://www.dir.ca.gov/oprl/2025-1/PWD/Determinations/Northern/NC-023-63-1.pdf
Note on C14: Franklin Gaudi: Labor Lead should always be $4 more than the Laborer

## Bid Schedule
Average PW Job - Example 6 | [10 empty] | Crew Info
[5 empty] | 8.25% | Project Tax Rate |  |  |  |  | 3 | multiplier (Laborers to Labor Lead)
[11 empty] | 7.5 | working hours per day
Bid # | Description | Quantity | Unit | Unit Price | Total | MARGIN | OUR COST | TOTAL COST | RESPONSIBLE PARTY |  |  |  | Category | Our Cost | Sale Price | Sale Price w/o Tax
[13 empty] | Overhead | 54559.3333 | 68690.64 | 68690.64
| Project OVERHEAD | Quantity | Unit | Unit Price | 68690.64 | 20.57% |  | 54559.3333 | LAW | Margin |  |  | Mob/Demob | 6000 | 7500 | 7500
| Bonding | 0 | EA | 27510 | 0 | 20% | 22000.62 | 0 | LAW | 20% | In-house |  | Labor | 68330 | 85419 | 85419
| Insurance | 0 | EA | 4590 | 0 | 20% | 3666.77 | 0 | LAW | 20% | Material |  | Materials | 68269.01 | 92379.4675 | 85339
| Restrooms | 3 | Months | 0 | 0 | 20% | 0 | 0 | LAW | 20% | Subs |  | Equipment | 950 | 1188 | 1188
| Administrative | 36 | HR | 94 | 3384 | 20% | 75 | 2700 | LAW | 20% | Equipment |  | Subs | 292900 | 366128 | 366128
| Project Management | 240 | HR | 107 | 25680 | 20% | 85 | 20400 | LAW | 20% | Other |  | Rental | 18725 | 25339.16 | 23408
| Permitting/Submittal Support | 150 | HR | 107 | 16050 | 20% | 85 | 12750 | LAW |  |  |  | Fuel | 11405 | 14259 | 14259
| PM Mileage | 2000 | Miles | 1.3 | 2600 | 20% | 1 | 2000 | LAW |  |  |  | Other | 47867.39 | 59836 | 59836
| Hotel Rooms (assumes 2-3 guys/room) | 51.4133 | Nights | 188 | 9665.7067 | 20% | 150 | 7712 | LAW
| Per Diem | 128.5333 | Days | 88 | 11310.9333 | 20% | 70 | 8997.3333 | LAW |  |  |  | Subtotals | 569005.7333 | 720739.2675 | 711767.64
| Other (Type it in here) | 0 | LS | 0 | 0 | 20% | 0 | 0 | LAW | [6 empty] | 8971.6275 | Sales Tax $
[16 empty] | 8.25% | Sales Tax % (back-calculated)
| BID SCHEDULE ITEMS | [14 empty] | 20.06% | Margin (back-calculated)
1 | Mob/Demob | Quantity | Unit | Unit Price | 51396 |  | Our Cost | 41115.395 | RESPONSIBLE PARTY | [6 empty] | 142761.9067 | Margin $
| Mobilization/Demobilization | 1 | EA | 7500 | 7500 | 20% | 6000 | 6000 |  | Labor Hrs | Labor days |  | Crew days | Crew weeks
| Labor | 1 | LS | 7998 | 7998 | 20% | 6398.16 | 6398.16 |  | 964 | 128.5333 |  | 32.1333 | 6.4267
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 7500 | 7500 | 20% | 6000 | 6000
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 688 | 688 | 20% | 550 | 550
| Other | 1 | LS | 27710 | 27710 | 20% | 22167.235 | 22167.235
Blank
2 | Site Demo | Quantity | Unit | Unit Price | 38068 |  | Our Cost | 30454.14 | RESPONSIBLE PARTY
| Labor | 1 | LS | 2021 | 2021 | 20% | 1616.64 | 1616.64
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 36047 | 36047 | 20% | 28837.5 | 28837.5
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
3 | Clearing, Grubbing, Stripping & Tree Removal | Quantity | Unit | Unit Price | 18736.25 |  | Our Cost | 14822.98 | RESPONSIBLE PARTY
| Labor | 1 | LS | 4014 | 4014 | 20% | 3210.48 | 3210.48
| Materials | 1 | LS | 2500 | 2706.25 | 20% | 2000 | 2000
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 12016 | 12016 | 20% | 9612.5 | 9612.5
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
4 | Temporary Dewatering | Quantity | Unit | Unit Price | 59578.75 |  | Our Cost | 46507.48 | RESPONSIBLE PARTY
| Labor | 1 | LS | 385 | 385 | 20% | 307.48 | 307.48
| Materials | 1 | LS | 17500 | 18943.75 | 20% | 14000 | 14000
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 40250 | 40250 | 20% | 32200 | 32200
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
5 | SWPPP Compliance | Quantity | Unit | Unit Price | 30587.8225 |  | Our Cost | 23788.72 | RESPONSIBLE PARTY
| Labor | 1 | LS | 11455 | 11455 | 20% | 9163.72 | 9163.72
| Materials | 1 | LS | 4063 | 4398.1975 | 20% | 3250 | 3250
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 6250 | 6250 | 20% | 5000 | 5000
| Rental | 1 | LS | 6250 | 6765.625 | 20% | 5000 | 5000
| Fuel | 1 | LS | 1719 | 1719 | 20% | 1375 | 1375
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
6 | Coanda Screen | Quantity | Unit | Unit Price | 8663.375 |  | Our Cost | 6683.04 | RESPONSIBLE PARTY
| Labor | 1 | LS | 3354 | 3354 | 20% | 2683.04 | 2683.04
| Materials | 1 | LS | 3750 | 4059.375 | 20% | 3000 | 3000
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 1250 | 1250 | 20% | 1000 | 1000
7 | Weir Bypass | Quantity | Unit | Unit Price | 7680.01 |  | Our Cost | 5932.72 | RESPONSIBLE PARTY
| Labor | 1 | LS | 2666 | 2666 | 20% | 2132.72 | 2132.72
| Materials | 1 | LS | 1438 | 1556.635 | 20% | 1150 | 1150
| Equipment | 1 | LS | 188 | 188 | 20% | 150 | 150
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 1750 | 1894.375 | 20% | 1400 | 1400
| Fuel | 1 | LS | 1375 | 1375 | 20% | 1100 | 1100
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
8 | 6-inch C900 PVC Pipe | Quantity | Unit | Unit Price | 12421.9625 |  | Our Cost | 9530.16 | RESPONSIBLE PARTY
| Labor | 1 | LS | 4301 | 4301 | 20% | 3440.16 | 3440.16
| Materials | 1 | LS | 1988 | 2152.01 | 20% | 1590 | 1590
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 4157 | 4499.9525 | 20% | 3325 | 3325
| Fuel | 1 | LS | 1469 | 1469 | 20% | 1175 | 1175
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
9 | Earthwork | Quantity | Unit | Unit Price | 53650 |  | Our Cost | 42919.52 | RESPONSIBLE PARTY
| Labor | 1 | LS | 10837 | 10837 | 20% | 8669.52 | 8669.52
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 42813 | 42813 | 20% | 34250 | 34250
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
10 | Rock Slope Protection | Quantity | Unit | Unit Price | 44146 |  | Our Cost | 35316.36 | RESPONSIBLE PARTY
| Labor | 1 | LS | 1333 | 1333 | 20% | 1066.36 | 1066.36
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 42813 | 42813 | 20% | 34250 | 34250
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
11 | Native Rock | Quantity | Unit | Unit Price | 22740 |  | Our Cost | 18191.36 | RESPONSIBLE PARTY
| Labor | 1 | LS | 1333 | 1333 | 20% | 1066.36 | 1066.36
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 21407 | 21407 | 20% | 17125 | 17125
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
12 | Cast-in-Place Concrete | Quantity | Unit | Unit Price | 110948 |  | Our Cost | 88757.72 | RESPONSIBLE PARTY
| Labor | 1 | LS | 2666 | 2666 | 20% | 2132.72 | 2132.72
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 107032 | 107032 | 20% | 85625 | 85625
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 1250 | 1250 | 20% | 1000 | 1000
13 | Staff Gauge | Quantity | Unit | Unit Price | 4966.3125 |  | Our Cost | 3832.72 | RESPONSIBLE PARTY
| Labor | 1 | LS | 2666 | 2666 | 20% | 2132.72 | 2132.72
| Materials | 1 | LS | 2125 | 2300.3125 | 20% | 1700 | 1700
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
14 | 6-inch Gate Valve | Quantity | Unit | Unit Price | 9591.2775 |  | Our Cost | 7383.17 | RESPONSIBLE PARTY
| Labor | 1 | LS | 4301 | 4301 | 20% | 3440.16 | 3440.16
| Materials | 1 | LS | 4367 | 4727.2775 | 20% | 3493.01 | 3493.01
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 563 | 563 | 20% | 450 | 450
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
15 | Temporary Dewatering | Quantity | Unit | Unit Price | 88704.75 |  | Our Cost | 69807.635 | RESPONSIBLE PARTY
| Labor | 1 | LS | 385 | 385 | 20% | 307.48 | 307.48
| Materials | 1 | LS | 17500 | 18943.75 | 20% | 14000 | 14000
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 50000 | 50000 | 20% | 40000 | 40000
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 19376 | 19376 | 20% | 15500.155 | 15500.155
16 | Demo pipe | Quantity | Unit | Unit Price | 17050.1975 |  | Our Cost | 13371.16 | RESPONSIBLE PARTY
| Labor | 1 | LS | 5714 | 5714 | 20% | 4571.16 | 4571.16
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 4063 | 4398.1975 | 20% | 3250 | 3250
| Fuel | 1 | LS | 4438 | 4438 | 20% | 3550 | 3550
| Other | 1 | LS | 2500 | 2500 | 20% | 2000 | 2000
17 | 6-inch PVC pipe | Quantity | Unit | Unit Price | 9779.25 |  | Our Cost | 7473.36 | RESPONSIBLE PARTY
| Labor | 1 | LS | 4042 | 4042 | 20% | 3233.36 | 3233.36
| Materials | 1 | LS | 5300 | 5737.25 | 20% | 4240 | 4240
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
18 | Hard Rock Excavation | Quantity | Unit | Unit Price | 18744.01 |  | Our Cost | 14519.84 | RESPONSIBLE PARTY
| Labor | 1 | LS | 5119 | 5119 | 20% | 4094.84 | 4094.84
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 7188 | 7781.01 | 20% | 5750 | 5750
| Fuel | 1 | LS | 3344 | 3344 | 20% | 2675 | 2675
| Other | 1 | LS | 2500 | 2500 | 20% | 2000 | 2000
19 | Stilling well | Quantity | Unit | Unit Price | 7251 |  | Our Cost | 5563.04 | RESPONSIBLE PARTY
| Labor | 1 | LS | 3354 | 3354 | 20% | 2683.04 | 2683.04
| Materials | 1 | LS | 3600 | 3897 | 20% | 2880 | 2880
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
20 | Solar Mast | Quantity | Unit | Unit Price | 27771.01 |  | Our Cost | 21345.48 | RESPONSIBLE PARTY
| Labor | 1 | LS | 6582 | 6582 | 20% | 5265.48 | 5265.48
| Materials | 1 | LS | 13188 | 14276.01 | 20% | 10550 | 10550
| Equipment | 1 | LS | 1000 | 1000 | 20% | 800 | 800
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 663 | 663 | 20% | 530 | 530
| Other | 1 | LS | 5250 | 5250 | 20% | 4200 | 4200
21 | Level Transducer | Quantity | Unit | Unit Price | 9574.65 |  | Our Cost | 7130.4 | RESPONSIBLE PARTY
| Labor | 1 | LS | 893 | 893 | 20% | 714.4 | 714.4
| Materials | 1 | LS | 8020 | 8681.65 | 20% | 6416 | 6416
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
22 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
23 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
24 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
25 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
26 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
27 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
28 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
29 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
30 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
31 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
32 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
33 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
34 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0
35 | 0 | Quantity | Unit | Unit Price | 0 |  | Our Cost | 0 | RESPONSIBLE PARTY
| Labor | 1 | LS | 0 | 0 | 20% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 20% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 20% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 20% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 20% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 20% | 0 | 0
| Other | 1 | LS | 0 | 0 | 20% | 0 | 0

## Bid Bond
| 0% | buffer for bid bond (dependent on confidence in all bid items)
Job Cost Breakdown | Totals
Labor | 68330
Equipment Rental | 18725
Subs | 292900
Material | 68269.01
Overhead | 54559.3333
Profit | 151733.5342
Other | 66222.39
Total Uncompleted Work | 720739.2675
| 733354 | Estimate Project Total (for Bond, use a nice round number based on the "total uncompleted work" above)
| 3% | Performance Bond Premium %
| 0.5% | Assumed Insurance Cost
| 10% | Bid Bond % (see specs, used on application, typically 10%)

## Bid Item 1
[8 empty] | Bid Item Total | 41115.395 | OUR COST
Mob/Demob
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 1 | VENDOR 2 | Total | COMMENT/NOTES
| Mobilization/Demobilization | [7 empty] | 6000
1 | Mobilization |  | 3 |  | 1000 |  |  |  | 3000
2 | Demobilization |  | 3 |  | 1000 |  |  |  | 3000
3 | [8 empty] | 0
Add More | [8 empty] | 0
| Labor | [7 empty] | 6398.16
1 | Labor Lead |  | 24 | HR | 67.36 |  |  |  | 1616.64 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 72 | HR | 66.41 |  |  |  | 4781.52 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More | [8 empty] | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 6000
1 | Construction staking |  | 1 | LS | 6000 | Morrow Surveying |  |  | 6000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 550
1 | Diesel |  | 100 | gal | 5.5 |  |  |  | 550
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other (may sometimes include Bonds and Insurance) | [7 empty] | 22167.235
1 | Cleanup trash haul |  | 1 | LS | 2000 |  |  |  | 2000
2 | Bonds (75%) |  | 1 | LS | 16500.465 |  |  |  | 16500.465
3 | Insurance |  | 1 | LS | 3666.77 |  |  |  | 3666.77
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 2
[8 empty] | Bid Item Total | 30454.14 | OUR COST
Site Demo
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 1616.64
1 | Labor Lead |  | 24 | HR | 67.36 |  |  |  | 1616.64 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  |  | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on "Bid Schedule" tab.
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 28837.5
1 | Demo |  | 1 | LS | 28837.5 | BT Concrete |  |  | 28837.5
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 3
[8 empty] | Bid Item Total | 14822.98 | OUR COST
Clearing, Grubbing, Stripping & Tree Removal
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3210.48
1 | Labor Lead |  | 24 | HR | 67.36 |  |  |  | 1616.64 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 2000
1 | Tree protection fence and other enviro stuff, roll |  | 10 | EA | 200 |  |  |  | 2000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 9612.5
1 | Demo |  | 1 | LS | 9612.5 | BT Concrete |  |  | 9612.5
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 4
[8 empty] | Bid Item Total | 46507.48 | OUR COST
Temporary Dewatering
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 307.48
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  |  | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  | 4 | HR | 76.87 |  |  |  | 307.48
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 14000
1 | 24" or 30" dia. ADS N-12 pipe |  | 160 | LF | 50 | We need an estimate on this |  |  | 8000
2 | 45 deg elbow ADS N-12 |  | 2 | EA | 2000 | We need an estimate on this |  |  | 4000
3 | Sand bags |  | 1 | LS | 2000 |  |  |  | 2000
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0 |  | $ from DWR | 10000
8 | [8 empty] | 0 |  | ft from DWR | 12.5
9 | [8 empty] | 0 |  | $/ft DWR | 800
10 | [8 empty] | 0
Add More | [8 empty] | 0 |  | $/ft for this | 400
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 32200
1 | Install and maintain dewatering system |  | 1 | LS | 32200 | BT Concrete |  |  | 32200
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0 | Hard hats, etc.
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 5
[8 empty] | Bid Item Total | 23788.72 | OUR COST
SWPPP Compliance
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 9163.72
1 | Labor Lead |  | 20 | HR | 67.36 |  |  |  | 1347.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 60 | HR | 66.41 |  |  |  | 3984.6 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 94.64 |  |  |  | 757.12
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  | 40 | HR | 76.87 |  |  |  | 3074.8
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 3250
1 | Waddles |  | 1000 | LF | 2 |  |  |  | 2000
2 | Silt fence |  | 1000 | LF | 1.25 |  |  |  | 1250
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 5000
1 | SWPPP or equal |  | 1 | LS | 5000 | Verux |  |  | 5000 | Check with Coast Eng. - Seems less than 1 acre
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 5000
1 | Rattle plate |  | 2 | MO | 500 |  |  |  | 1000 | For equipment rates see this spreadsheet:
2 | Water truck |  | 1 | MO | 4000 |  |  |  | 4000 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1375
1 | Diesel |  | 250 | gal | 5.5 |  |  |  | 1375
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0 | Month
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 6
[8 empty] | Bid Item Total | 6683.04 | OUR COST
Coanda Screen
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 2683.04
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  | 8 | HR | 68.79 |  |  |  | 550.32
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 3000
1 | Coanda screen |  | 1 | LS | 1900 |  |  |  | 1900 | https://elginseparationsolutions.com/coanda-screens/
2 | Anchors |  | 1 | LS | 300 |  |  |  | 300
3 | Slide gate ( for 6" pipe) |  | 1 | LS | 600 |  |  |  | 600
4 | 6" C900 pipe starter |  | 10 | LF | 20 |  |  |  | 200
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 1000
1 | Misc. fasteners, acessories, etc. |  | 1 | LS | 1000 |  |  |  | 1000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 7
[8 empty] | Bid Item Total | 5932.72 | OUR COST
Weir Bypass
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 2132.72
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 1150
1 | 6x6 Pressure Treated (8' L) |  | 1 | LS | 150 |  |  |  | 150
2 | Whipps 510 Aluminum stop logs |  | 1 | LS | 500 | Whipps, Inc |  |  | 500 | Guess
3 | Anchors, fasteners, etc. |  | 1 | LS | 500 |  |  |  | 500
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 150
1 | Wood saw |  | 1 | WEEK | 150 |  |  |  | 150
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 1400
1 | Generator 56 kW |  | 1 | MO | 1400 |  |  |  | 1400 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1100
1 | Diesel |  | 200 | gal | 5.5 |  |  |  | 1100
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 8
[8 empty] | Bid Item Total | 9530.16 | OUR COST
6-inch C900 PVC Pipe
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3440.16
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 94.64 |  |  |  | 757.12
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  | 8 | HR | 68.79 |  |  |  | 550.32
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 1590
1 | 6" C900 DR-25 |  | 15 | LF | 20 | JM Eagle |  |  | 300
2 | 4" S80 |  | 20 | LF | 7 |  |  |  | 140
3 | 4" PERF PVC |  | 10 | LF | 5 |  |  |  | 50 | PERF DRAIN PIPE 4" X 10' : 9910-550250
4 | MISC |  | 1 | EA | 100 |  |  |  | 100
5 | Imported sand |  | 10 | TON | 100 |  |  |  | 1000
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 3325
1 | Mini ex (308) |  | 0.5 | MO | 6000 |  |  |  | 3000 | For equipment rates see this spreadsheet:
2 | Jumping jack |  | 0.5 | MO | 650 |  |  |  | 325 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1175
1 | Diesel |  | 200 | gal | 5.5 |  |  |  | 1100
2 | Gas |  | 15 | gal | 5 |  |  |  | 75
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 9
[8 empty] | Bid Item Total | 42919.52 | OUR COST
Earthwork
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 8669.52
1 | Labor Lead |  | 24 | HR | 67.36 |  |  |  | 1616.64 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 72 | HR | 66.41 |  |  |  | 4781.52 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 24 | HR | 94.64 |  |  |  | 2271.36
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 34250
1 | BT concrete (20%) of line item |  | 1 | LS | 34250 | BT concrete |  |  | 34250
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal | 5.5 |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 10
[8 empty] | Bid Item Total | 35316.36 | OUR COST
Rock Slope Protection
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 1066.36
1 | Labor Lead |  | 4 | HR | 67.36 |  |  |  | 269.44 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 12 | HR | 66.41 |  |  |  | 796.92 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 34250
1 | BT concrete (20%) of line item |  | 1 | LS | 34250 | BT concrete |  |  | 34250
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal | 5.5 |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 11
[8 empty] | Bid Item Total | 18191.36 | OUR COST
Native Rock
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 1066.36
1 | Labor Lead |  | 4 | HR | 67.36 |  |  |  | 269.44 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 12 | HR | 66.41 |  |  |  | 796.92 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 17125
1 | BT concrete (10%) of line item |  | 1 | LS | 17125 | BT concrete |  |  | 17125
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal | 5.5 |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 12
[8 empty] | Bid Item Total | 88757.72 | OUR COST
Cast-in-Place Concrete
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 2132.72
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 85625
1 | BT concrete (50%) of line item |  | 1 | LS | 85625 | BT concrete |  |  | 85625
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 1000
1 | Cleanup |  | 1 | LS | 1000 |  |  |  | 1000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 13
[8 empty] | Bid Item Total | 3832.72 | OUR COST
Staff Gauge
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 2132.72
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 1700
1 | 8' Staff gauge |  | 1 | LS | 700 |  |  |  | 700
2 | Staff gauge mount |  | 1 | LS | 700 |  |  |  | 700
3 | Misc. anchors |  | 1 | LS | 300 |  |  |  | 300
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 14
[8 empty] | Bid Item Total | 7383.17 | OUR COST
6-inch Gate Valve
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3440.16
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 94.64 |  |  |  | 757.12
4 | Electrician |  | 0 | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  | 8 | HR | 68.79 |  |  |  | 550.32
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 3493.01
1 | 6" gate valve |  | 1 | EA | 1163.01 | PACE (Quote# 2427185) |  |  | 1163.01 | Mueller A2361, or M&H Style 4067; QUOTED: 6 FLG X FLG C-515 GATE VALVE A-2361 MUELLER
2 | 8" PVC Riser |  | 4 | LF | 20 |  |  |  | 80
3 | Box (Christy G5) |  | 1 | LS | 150 | PACE (Quote #: NV25-0479) |  |  | 150 | G5 BOX = 68.00 ; G5 LID = 50.00
4 | Nut extension |  | 1 | LS | 200 |  |  |  | 200
5 | 6" flange adapters |  | 2 | EA | 450 |  |  |  | 900
6 | Misc. gaskets, bolt, etc. |  | 1 | LS | 1000 |  |  |  | 1000
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 450
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  | 100 | gal | 4.5 |  |  |  | 450
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 15
[8 empty] | Bid Item Total | 69807.635 | OUR COST
Temporary Dewatering
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 307.48
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  |  | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  | 4 | HR | 76.87 |  |  |  | 307.48
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 14000
1 | 24" or 30" dia. ADS N-12 pipe |  | 160 | LF | 50 |  |  |  | 8000
2 | 45 deg elbow ADS N-12 |  | 2 | EA | 2000 |  |  |  | 4000
3 | Sand bags |  | 1 | LS | 2000 |  |  |  | 2000
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 40000
1 | Install and maintain dewatering system |  | 1 | LS | 40000 | BT concrete |  |  | 40000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 15500.155
1 | Bonds (75%) |  | 1 | LS | 5500.155 |  |  |  | 5500.155
2 | Contingency |  | 1 | LS | 10000 |  |  |  | 10000
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 16
[8 empty] | Bid Item Total | 13371.16 | OUR COST
Demo pipe
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 4571.16
1 | Labor Lead |  | 12 | HR | 67.36 |  |  |  | 808.32 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 36 | HR | 66.41 |  |  |  | 2390.76 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 94.64 |  |  |  | 757.12
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  | 8 | HR | 76.87 |  |  |  | 614.96
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 3250
1 | Large Excavator (89k) |  | 0.25 | MO | 8500 |  |  |  | 2125 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Wheel loader |  | 0.25 | MO | 4500 |  |  |  | 1125
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 3550
1 | Diesel |  | 600 | gal | 5.5 |  |  |  | 3300
2 | Gas |  | 50 | gal | 5 |  |  |  | 250
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 2000
1 | Spoil export (fill on-site) see 31 11 00.5 (Part 3.06) |  | 0 | CY | 50 |  |  |  | 0
2 | Roll-offs |  | 1 | LS | 2000 |  |  |  | 2000
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 17
[8 empty] | Bid Item Total | 7473.36 | OUR COST
6-inch PVC pipe
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3233.36
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  | 16 | HR | 68.79 |  |  |  | 1100.64
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 4240
1 | 6" C900 DR-25 |  | 57 | LF | 20 | JM Eagle |  |  | 1140
2 | 6" 22.5 elbow |  | 2 | EA | 50 | JM Eagle |  |  | 100
3 | Thrust block concrete |  | 2 | EA | 0 |  |  |  | 0
4 | restraints |  | 1 | LS | 2000 |  |  |  | 2000
5 | Imported sand |  | 10 | TON | 100 |  |  |  | 1000
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 18
[8 empty] | Bid Item Total | 14519.84 | OUR COST
Hard Rock Excavation
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 4094.84
1 | Labor Lead |  | 4 | HR | 67.36 |  |  |  | 269.44 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 12 | HR | 66.41 |  |  |  | 796.92 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 32 | HR | 94.64 |  |  |  | 3028.48
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 5750
1 | Large Excavator (89k) |  | 0.25 | MO | 8500 |  |  |  | 2125 | For equipment rates see this spreadsheet:
2 | Excavator breaker attachment |  | 0.25 | MO | 2500 |  |  |  | 625 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Wheel loader |  | 0.25 | MO | 4500 |  |  |  | 1125
4 | Grizzly bar screen |  | 0.25 | MO | 4500 |  |  |  | 1125
Add More | Jack hammer and air compressor |  | 0.25 | MO | 3000 |  |  |  | 750 | Guess
End | [8 empty] | 0
| Fuel | [7 empty] | 2675
1 | Diesel |  | 450 | gal | 5.5 |  |  |  | 2475
2 | Gas |  | 40 | gal | 5 |  |  |  | 200
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 2000
1 | Haul-off |  | 1 | LS | 2000 |  |  |  | 2000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 19
[8 empty] | Bid Item Total | 5563.04 | OUR COST
Stilling well
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 2683.04
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  | 8 | HR | 68.79 |  |  |  | 550.32
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 2880
1 | 6" SCH80 PVC |  | 20 | LF | 30 |  |  |  | 600
2 | 6" tee |  | 1 | EA | 40 |  |  |  | 40
3 | 6" cap |  | 3 | EA | 30 |  |  |  | 90
4 | Stainless unistrut |  | 1 | LS | 500 |  |  |  | 500
5 | Strut clamps |  | 1 | LS | 500 |  |  |  | 500
6 | 4" Perf pipe, SCH80 |  | 1 | LS | 200 |  |  |  | 200
7 | Carson 02 15"x19"x36" HDPE box w/ cover |  | 1 | LS | 500 |  |  |  | 500
8 | J-box |  | 1 | LS | 150 |  |  |  | 150
9 | Misc. anchors |  | 1 | LS | 300 |  |  |  | 300
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 20
[8 empty] | Bid Item Total | 21345.48 | OUR COST
Solar Mast
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 5265.48
1 | Labor Lead |  | 8 | HR | 67.36 |  |  |  | 538.88 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 66.41 |  |  |  | 1593.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  | 32 | HR | 89.3 |  |  |  | 2857.6
5 | Pipe Fitter |  | 4 | HR | 68.79 |  |  |  | 275.16
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 10550
1 | #4 rebar |  | 1 | LS | 200 |  |  |  | 200
2 | Concrete |  | 1 | LS | 200 |  |  |  | 200
3 | PVC coated RGS conduit |  | 20 | LF | 50 |  |  |  | 1000 | 1"???
4 | 4" dia. GRS conduit (20') |  | 1 | LS | 500 |  |  |  | 500
5 | Battery enclosure |  | 1 | LS | 1500 |  |  |  | 1500
6 | Solar brackets |  | 1 | LS | 500 |  |  |  | 500
7 | Solar arrays |  | 1 | LS | 2000 |  |  |  | 2000
9 | Groundwell |  | 1 | LS | 600 |  |  |  | 600
10 | Sand for backfill |  | 5 | CY | 120 |  |  |  | 600
11 | Conduit and pull tape |  | 1 | LS | 200 |  |  |  | 200
12 | Wire/cable |  | 1 | LS | 500 |  |  |  | 500
13 | Battery charge controller |  | 1 | LS | 750 |  |  |  | 750
Add More | Batteries |  | 1 | LS | 2000 |  |  |  | 2000
End | [8 empty] | 0
| Equipment | [7 empty] | 800
1 | Hand auger |  | 1 | WEEK | 300 |  |  |  | 300
2 | Mini ex for trencha and backfill |  | 0.25 | MO | 2000 |  |  |  | 500
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 530
1 | Diesel |  | 60 | gal | 5.5 |  |  |  | 330
2 | Gas |  | 40 | gal | 5 |  |  |  | 200
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 4200
1 | Laurel shop assembly and testing fee (offsite) |  | 1 | LS | 1200 |  |  |  | 1200
2 | Automation team integration fee (offsite) |  | 1 | LS | 3000 |  |  |  | 3000
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 21
[8 empty] | Bid Item Total | 7130.4 | OUR COST
Level Transducer
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 714.4
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  | 8 | HR | 89.3 |  |  |  | 714.4
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 6416
1 | Transducer |  | 1 | LS | 1200 |  |  |  | 1200
2 | Misc. |  | 1 | LS | 300 |  |  |  | 300
3 | Conduit, fittings, enclosures, etc. |  | 1 | LS | 500 |  |  |  | 500
4 | [8 empty] | 0
5 | XIO SYSTEM | [7 empty] | 0
6 | Opto RIO 8 Inputs 2 Outputs and Hardware groov RIO MM1 with Remote Universal I/O; 8 software-configurable channels; 2 form C electromechanical relay output channels, Wiring Harness and Terminal Blocks, mounted on a back panel. |  | 1 |  | 2200 | XIO |  |  | 2200
7 | Cellular Modem Cellular modem mounted on a back panel. |  | 1 |  | 900 |  |  |  | 900
8 | Communications Cellular Internet Service |  | 1 |  | 564 |  |  |  | 564
9 | Asset, Monitored Input for the Level Transducer and display on the ACUITY interface |  | 1 |  | 252 |  |  |  | 252
10 | Submittal XiO Engineering will author a Submittal Document including Lists and descriptions of XiO-Supplied hardware, control logic descriptions, XiO Wiring Diagrams, and Cut Sheets for all hardware supplied by XiO. |  | 5 |  | 100 |  |  |  | 500
| Automation Hardware Programming and Testing Connection to the XiO Cloud |  | 25 |  | 100
| Panel Fabrication Fabrication of custom control panels with control and communications hardware, where applicable. |  | 4 |  | 100
| Remote Installation Support |  | 4 |  | 100
| Cloud Design and Development Design and Development of Dashboards, Panels, Alarms, Asset Registry, Reports, and other custom Cloud components, if applicable. |  | 25 |  | 100
| Annual Subscription Fee: |  | 1 |  | 816 |  |  |  |  | -->>
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 22
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 23
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 24
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 25
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 26
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 27
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 28
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 29
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 30
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 31
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 32
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 33
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 34
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 35
[8 empty] | Bid Item Total | 0 | OUR COST
0
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 67.36 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 66.41 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 94.64 |  |  |  | 0
4 | Electrician |  |  | HR | 89.3 |  |  |  | 0
5 | Pipe Fitter |  |  | HR | 68.79 |  |  |  | 0
6 | Truck Driver |  |  | HR | 76.87 |  |  |  | 0
7 | Landscaper |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials (without tax) | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental (without tax) | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | gal |  |  |  |  | 0
2 | Gas |  |  | gal |  |  |  |  | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0