## Bid Summary
| Example 3D |  |  |  |  | 4608257 |  | 5072261 | Total bid Amount
UPDATE VALUES IN YELLOW |  |  | *Some agencies use a special code to identify the Bid Schedule
|  |  | Code* | Bid Schedule |  | Total with margin | Overhead | Total with overhead | QTY | Unit | Unit cost | Subtotals | Notes
| Notes |  | D-1 | 1 | Lateral DE Connection (36-inch Steel at STA 10+00) | 54800 | 12888.8889 | 67689 | 1 | LS | 67689 |  |  | 67689 | 67689
|  |  | D-1 | 2 | Lateral DE-B Connection (12-inch Asbestos-Cement at STA 34+29.21) | 21600 | 12888.8889 | 34489 | 1 | LS | 34489 |  |  | 34489 | 34489
Bid date: | 2025-05-30 |  | D-1 | 3 | Lateral DE-1 Connection (27-inch Steel at STA 35+94.05) | 24500 | 12888.8889 | 37389 | 1 | LS | 37389 |  |  | 37389 | 37389
Award date: | 2025-06-15 |  | D-1 | 4 | DE-1 BPS Connection (18-inch Steel at STA 10+74.99) | 41700 | 12888.8889 | 54589 | 1 |  | 54589 |  |  | 54589 | 54589
Notice date: | 2025-07-15 |  | D-1 | 5 | Lateral DE-1-A-1 Connection (15-inch Asbestos-Cement at STA 50+22.34) | 31500 | 12888.8889 | 44389 | 1 |  | 44389 |  |  | 44389 | 44389
Start Date: | 2025-07-17 |  | D-1 | 6 | Lateral DE-1-A Connection (21-inch Asbestos-Cement at STA 51+04.05) | 24200 | 12888.8889 | 37089 | 1 |  | 37089 |  |  | 37089 | 37089
Complete by: | 2026-01-31 |  | D-1 | 7 | Removal and Disposal of Existing Laterals (Lat DE, Lat DE-1, Lat DE-1-A, and BPS Steel Pipe on C-101, C-301, C-302, C-304, C-305, C-402, C-403) | 66800 | 12888.8889 | 79689 | 1 |  | 79689 |  |  | 79689 | 79689
|  |  | D-1 | 8 | Removal and Disposal of Existing Laterals and Turnout Connections (Asbestos Cement Pipe on C-302 and C-305) | 42600 | 12888.8889 | 55489 | 1 |  | 55489 |  |  | 55489 | 55489
Work Days: | 198 | (including weekends) | D-1 | 9 | Removal and Disposal of Existing Turnout Connections (PVC Pipe on C-402 and C-403) | 7000 | 12888.8889 | 19889 | 1 |  | 19889 |  |  | 19889 | 19889
|  |  | D-1 | 10 | Removal and Disposal of Existing Marker Posts and Cathodic Protection Test Stations | 22800 | 12888.8889 | 35689 | 7 |  | 5098.4286 |  |  | 5099 | 35693
|  |  | D-1 | 11 | 30-inch PVC Pipe (Lateral DE-1-A) | 875290 | 12888.8889 | 888179 | 4105 |  | 216.3652 |  |  | 217 | 890785
| 1000 | Liquidated Damages ($/day) | D-1 | 12 | 36-inch PVC Pipe (Lateral DE-1) | 742390 | 12888.8889 | 755279 | 2595 |  | 291.0516 |  |  | 292 | 757740
|  |  | D-1 | 13 | 42-inch Steel Pipe (Lateral DE) | 1227877 | 12888.8889 | 1240766 | 2544 |  | 487.7225 |  |  | 488 | 1241472
|  |  | D-1 | 14 | Connection to Turnout 14D (14-inch PVC at STA 17+67.77) | 15900 | 12888.8889 | 28789 | 1 |  | 28789 |  |  | 28789 | 28789
|  |  | D-1 | 15 | Connection to Turnout 12D (10-inch Asbestos-Cement at STA 34+14.45) | 13300 | 12888.8889 | 26189 | 1 |  | 26189 |  |  | 26189 | 26189
|  |  | D-1 | 16 | Connection to Turnout 28D (10-inch PVC at STA 24+42.80) | 25800 | 12888.8889 | 38689 | 1 |  | 38689 |  |  | 38689 | 38689
|  |  | D-1 | 17 | 10-inch Buried Service Butterfly Valve Assembly | 61400 | 12888.8889 | 74289 | 4 |  | 18572.25 |  |  | 18573 | 74292
| 464000 | Project Overhead to be dispersed | D-1 | 18 | 12-inch Buried Service Butterfly Valve Assembly | 27100 | 12888.8889 | 39989 | 1 |  | 39989 |  |  | 39989 | 39989
| 36 | Number of Bid Items to spread overhead | D-1 | 19 | 14-inch Buried Service Butterfly Valve Assembly | 24500 | 12888.8889 | 37389 | 1 |  | 37389 |  |  | 37389 | 37389
|  |  | D-1 | 20 | 30-inch Buried Service Butterfly Valve Assembly | 95400 | 12888.8889 | 108289 | 1 |  | 108289 |  |  | 108289 | 108289
|  |  | D-1 | 21 | 36-inch Buried Service Butterfly Valve Assembly | 94200 | 12888.8889 | 107089 | 1 |  | 107089 |  |  | 107089 | 107089
| 12888.8889 | Overhead $$ / site | D-1 | 22 | 2-inch Underground Combination Air Valve Assembly | 56000 | 12888.8889 | 68889 | 2 |  | 34444.5 |  |  | 34445 | 68890
|  |  | D-1 | 23 | 3-inch Underground Combination Air Valve Assembly | 65700 | 12888.8889 | 78589 | 2 |  | 39294.5 |  |  | 39295 | 78590
| 9.148% | Overhead as a % of Total | D-1 | 24 | 6-inch Underground Combination Air Valve Assembly | 61300 | 12888.8889 | 74189 | 1 |  | 74189 |  |  | 74189 | 74189
|  |  | D-1 | 25 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe (Materials) | 159600 | 12888.8889 | 172489 | 1 |  | 172489 |  |  | 172489 | 172489
|  |  | D-1 | 26 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Open Cut Installation) | 205800 | 12888.8889 | 218689 | 1 |  | 218689 |  |  | 218689 | 218689
|  |  | D-1 | 27 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Annular Space Backfill) | 83000 | 12888.8889 | 95889 | 1 |  | 95889 |  |  | 95889 | 95889
|  |  | D-1 | 28 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Cathodic Protection System) | 43600 | 12888.8889 | 56489 | 1 |  | 56489 |  |  | 56489 | 56489
|  |  | D-1 | 29 | Valve Cathodic Protection (Lat DE) | 35600 | 12888.8889 | 48489 | 3 |  | 16163 |  |  | 16163 | 48489
|  |  | D-1 | 30 | Valve Cathodic Protection Test Station (Lat DE) | 43200 | 12888.8889 | 56089 | 3 |  | 18696.3333 |  |  | 18697 | 56091
|  |  | D-1 | 31 | Flange Insulation Kits (Lat DE and Lat DE-1) | 17600 | 12888.8889 | 30489 | 1 |  | 30489 |  |  | 30489 | 30489
|  |  | D-1 | 32 | Flange Insulation Cathodic Protection Test Station (Lat DE) | 86600 | 12888.8889 | 99489 | 3 |  | 33163 |  |  | 33163 | 99489
|  |  | D-1 | 33 | Color Coded Marker Posts | 25200 | 12888.8889 | 38089 | 13 |  | 2929.9231 |  |  | 2930 | 38090
|  |  | D-1 | 34 | Hydrostatic Pressure Testing (30-inch Lateral DE-1-A and Connections) | 55900 | 12888.8889 | 68789 | 1 |  | 68789 |  |  | 68789 | 68789
|  |  | D-1 | 35 | Hydrostatic Pressure Testing (36-inch Lateral DE-1 and Connections) | 48800 | 12888.8889 | 61689 | 1 |  | 61689 |  |  | 61689 | 61689
|  |  | D-1 | 36 | Hydrostatic Pressure Testing (42-inch Lateral DE and Connections) | 79700 | 12888.8889 | 92589 | 1 |  | 92589 |  |  | 92589 | 92589
|  |  | D-1 | 37 |  |  | 0 | 0 |  |  | #DIV/0! |  |  |  | 5078046
[7 empty] | 464000 | (check against Cell B21)

## Prevailing Wage
Step #1
Review the Plan Set and the Specifications to identify the type of work that will be done.
Step #2
Use this link to identify potential wage determinations for those jobs:
*Ensure you are in the correct county.
https://www.dir.ca.gov/oprl/2024-1/PWD/Determinations/Subtrades/jrnylist.html
Step #3
List the Classification as well as the corresponding wage determinations:
| Classification | Wage ($/hr) | Jobs/Tasks | Justification | Task Code (if used)
1 | Labor Lead | 74.69
2 | Laborer | 71.69
3 | Operator | 96.29
4 | Driver | 76.71
5 | Landscaper
6 | Pipefitter | 87.69
7 | Etc
8 | Etc
*For justification, see "Scope of Work Provisions" link in the wage determinations from the link above.
*Wage is non-overtime.

## Bid Schedule
Example 3D | [10 empty] | Crew Info
[11 empty] | 3 | multiplier (helpers to leadman)
[11 empty] | 8 | working hours per day
Bid # | Description | Quantity | Unit | Unit Price | Total | MARGIN | OUR COST | TOTAL COST | RESPONSIBLE PARTY |  |  |  | Category | Our Cost | Sale Price
[13 empty] | Overhead | 353234.5175 | 464000
| Project OVERHEAD | Quantity | Unit | Unit Price | 464000 | 23.87% |  | 353234.5175 | LAW | Margin |  |  | Mob/Demob | 0 | 0
| Bonding | 1 | EA | 189500 | 189500 | 18% | 155334.5175 | 155334.5175 | LAW | 18% | In-house |  | Labor | 686778.5 | 839510
| Insurance | 1 | EA | 5500 | 5500 | 18% | 4500 | 4500 | LAW | 25% | Material |  | Materials | 2267455.99 | 3024270
| Restrooms | 12 | Months | 1500 | 18000 | 18% | 1200 | 14400 | LAW | 18% | Subs |  | Equipment | 25560 | 31700
| Administrative | 200 | HR | 200 | 40000 | 18% | 120 | 24000 | LAW | 18% | Equipment |  | Subs | 252928 | 308727
| Project Management | 1000 | HR | 100 | 100000 | 18% | 70 | 70000 | LAW | 18% | Other |  | Rental | 149925.3 | 184170
| Permitting/Submittal Support | 500 | HR | 100 | 50000 | 18% | 70 | 35000 | LAW |  |  |  | Fuel | 137160 | 183680
| PM Fuel | 1 | LS | 6100 | 6100 | 18% | 5000 | 5000 | LAW |  |  |  | Other | 29404.5 | 36200
| Misc Handling Equipment | 1 | Days | 54900 | 54900 | 18% | 45000 | 45000 | LAW
| Per Diem | 1 | Days | 0 | 0 | 18% | 0 | 0 | LAW |  |  |  | Subtotal | 3902446.8075 | 5072257
[14 empty] | 23.06% | Margin (back-calculated)
BID SCHEDULE ITEMS
1 | Lateral DE Connection (36-inch Steel at STA 10+00) | Quantity | Unit | Unit Price | 54800 |  | Our Cost | 42209.01 | [6 empty] | 1169810.1925
| Mobilization/Demobilization | 1 | EA | 0 | 0 | 18% | 0 | 0 |  | Labor Hrs | Labor days |  | Crew days | Crew weeks
| Labor | 1 | LS | 9100 | 9100 | 18% | 7404.16 | 7404.16 |  | 8432 | 1054 |  | 263.5 | 52.7
| Materials | 1 | LS | 33600 | 33600 | 25% | 25200 | 25200
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 7400 | 7400 | 18% | 6000 | 6000
| Rental | 1 | LS | 2000 | 2000 | 18% | 1614.85 | 1614.85
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 700 | 700 | 18% | 550 | 550
Blank
2 | Lateral DE-B Connection (12-inch Asbestos-Cement at STA 34+29.21) | Quantity | Unit | Unit Price | 21600 |  |  | 17148.56
| Labor | 1 | LS | 14400 | 14400 | 18% | 11738.96 | 11738.96
| Materials | 1 | LS | 2300 | 2300 | 25% | 1678.25 | 1678.25
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 2200 | 2200 | 18% | 1741.35 | 1741.35
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 700 | 700 | 18% | 550 | 550
3 | Lateral DE-1 Connection (27-inch Steel at STA 35+94.05) | Quantity | Unit | Unit Price | 24500 |  |  | 19085.73
| Labor | 1 | LS | 10100 | 10100 | 18% | 8281.06 | 8281.06
| Materials | 1 | LS | 8900 | 8900 | 25% | 6653.77 | 6653.77
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 1300 | 1300 | 18% | 1000 | 1000
| Rental | 1 | LS | 1500 | 1500 | 18% | 1160.9 | 1160.9
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 700 | 700 | 18% | 550 | 550
4 | DE-1 BPS Connection (18-inch Steel at STA 10+74.99) | Quantity | Unit | Unit Price | 41700 |  |  | 32280.74
| Labor | 1 | LS | 14700 | 14700 | 18% | 11983.14 | 11983.14
| Materials | 1 | LS | 22000 | 22000 | 25% | 16456.75 | 16456.75
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 2100 | 2100 | 18% | 1680.85 | 1680.85
| Fuel | 1 | LS | 2900 | 2900 | 25% | 2160 | 2160
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
5 | Lateral DE-1-A-1 Connection (15-inch Asbestos-Cement at STA 50+22.34) | Quantity | Unit | Unit Price | 31500 |  |  | 24203.56
| Labor | 1 | LS | 9100 | 9100 | 18% | 7404.16 | 7404.16
| Materials | 1 | LS | 20900 | 20900 | 25% | 15638.5 | 15638.5
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1500 | 1500 | 18% | 1160.9 | 1160.9
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
6 | Lateral DE-1-A Connection (21-inch Asbestos-Cement at STA 51+04.05) | Quantity | Unit | Unit Price | 24200 |  |  | 18649.31
| Labor | 1 | LS | 9100 | 9100 | 18% | 7404.16 | 7404.16
| Materials | 1 | LS | 11600 | 11600 | 25% | 8644.25 | 8644.25
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1500 | 1500 | 18% | 1160.9 | 1160.9
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
7 | Removal and Disposal of Existing Laterals (Lat DE, Lat DE-1, Lat DE-1-A, and BPS Steel Pipe on C-101, C-301, C-302, C-304, C-305, C-402, C-403) | Quantity | Unit | Unit Price | 66800 |  |  | 52821.26
| Labor | 1 | LS | 30600 | 30600 | 18% | 25018.56 | 25018.56
| Materials | 1 | LS | 20000 | 20000 | 25% | 15000 | 15000
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 4300 | 4300 | 18% | 3482.7 | 3482.7
| Fuel | 1 | LS | 5800 | 5800 | 25% | 4320 | 4320
| Other | 1 | LS | 6100 | 6100 | 18% | 5000 | 5000
8 | Removal and Disposal of Existing Laterals and Turnout Connections (Asbestos Cement Pipe on C-302 and C-305) | Quantity | Unit | Unit Price | 42600 |  |  | 33502.53
| Labor | 1 | LS | 4600 | 4600 | 18% | 3702.08 | 3702.08
| Materials | 1 | LS | 16000 | 16000 | 25% | 12000 | 12000
| Equipment | 1 | LS | 1900 | 1900 | 18% | 1500 | 1500
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 800 | 800 | 18% | 580.45 | 580.45
| Fuel | 1 | LS | 1000 | 1000 | 25% | 720 | 720
| Other | 1 | LS | 18300 | 18300 | 18% | 15000 | 15000
9 | Removal and Disposal of Existing Turnout Connections (PVC Pipe on C-402 and C-403) | Quantity | Unit | Unit Price | 7000 |  |  | 5388.85
| Labor | 1 | LS | 3800 | 3800 | 18% | 3088.4 | 3088.4
| Materials | 1 | LS | 700 | 700 | 25% | 500 | 500
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 800 | 800 | 18% | 580.45 | 580.45
| Fuel | 1 | LS | 1000 | 1000 | 25% | 720 | 720
| Other | 1 | LS | 700 | 700 | 18% | 500 | 500
10 | Removal and Disposal of Existing Marker Posts and Cathodic Protection Test Stations | Quantity | Unit | Unit Price | 22800 |  |  | 18225.72
| Labor | 1 | LS | 12500 | 12500 | 18% | 10185.72 | 10185.72
| Materials | 1 | LS | 700 | 700 | 25% | 500 | 500
| Equipment | 1 | LS | 3600 | 3600 | 18% | 2880 | 2880
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 2900 | 2900 | 25% | 2160 | 2160
| Other | 1 | LS | 3100 | 3100 | 18% | 2500 | 2500
11 | 30-inch PVC Pipe (Lateral DE-1-A) | Quantity | Unit | Unit Price | 875290 |  |  | 668072.8
| Labor | 1 | LS | 109090 | 109090 | 18% | 89448 | 89448
| Materials | 1 | LS | 645300 | 645300 | 25% | 483969.8 | 483969.8
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 56900 | 56900 | 18% | 46655 | 46655
| Fuel | 1 | LS | 64000 | 64000 | 25% | 48000 | 48000
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
12 | 36-inch PVC Pipe (Lateral DE-1) | Quantity | Unit | Unit Price | 742390 |  |  | 563360.82
| Labor | 1 | LS | 76360 | 76360 | 18% | 62613.6 | 62613.6
| Materials | 1 | LS | 603430 | 603430 | 25% | 452569.72 | 452569.72
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 17800 | 17800 | 18% | 14577.5 | 14577.5
| Fuel | 1 | LS | 44800 | 44800 | 25% | 33600 | 33600
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
13 | 42-inch Steel Pipe (Lateral DE) | Quantity | Unit | Unit Price | 1227877 |  |  | 937177
| Labor | 1 | LS | 59060 | 59060 | 18% | 48422 | 48422
| Materials | 1 | LS | 987540 | 987540 | 25% | 740652 | 740652
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 161327 | 161327 | 18% | 132288 | 132288
| Rental | 1 | LS | 12270 | 12270 | 18% | 10055 | 10055
| Fuel | 1 | LS | 7680 | 7680 | 25% | 5760 | 5760
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
14 | Connection to Turnout 14D (14-inch PVC at STA 17+67.77) | Quantity | Unit | Unit Price | 15900 |  |  | 12599.1
| Labor | 1 | LS | 10800 | 10800 | 18% | 8807.2 | 8807.2
| Materials | 1 | LS | 1600 | 1600 | 25% | 1191 | 1191
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1500 | 1500 | 18% | 1160.9 | 1160.9
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
15 | Connection to Turnout 12D (10-inch Asbestos-Cement at STA 34+14.45) | Quantity | Unit | Unit Price | 13300 |  |  | 10469.22
| Labor | 1 | LS | 8400 | 8400 | 18% | 6878.32 | 6878.32
| Materials | 1 | LS | 1400 | 1400 | 25% | 990 | 990
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1500 | 1500 | 18% | 1160.9 | 1160.9
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
16 | Connection to Turnout 28D (10-inch PVC at STA 24+42.80) | Quantity | Unit | Unit Price | 25800 |  |  | 19767.7
| Labor | 1 | LS | 7600 | 7600 | 18% | 6176.8 | 6176.8
| Materials | 1 | LS | 14700 | 14700 | 25% | 10990 | 10990
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 1500 | 1500 | 18% | 1160.9 | 1160.9
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1440 | 1440
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
17 | 10-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 61400 |  |  | 47152.53
| Labor | 1 | LS | 15900 | 15900 | 18% | 12967.28 | 12967.28
| Materials | 1 | LS | 40200 | 40200 | 25% | 30128 | 30128
| Equipment | 1 | LS | 2400 | 2400 | 18% | 1920 | 1920
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 300 | 300 | 18% | 217.25 | 217.25
| Fuel | 1 | LS | 2600 | 2600 | 25% | 1920 | 1920
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
18 | 12-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 27100 |  |  | 20904.73
| Labor | 1 | LS | 8300 | 8300 | 18% | 6790.48 | 6790.48
| Materials | 1 | LS | 16000 | 16000 | 25% | 11977 | 11977
| Equipment | 1 | LS | 1200 | 1200 | 18% | 960 | 960
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 300 | 300 | 18% | 217.25 | 217.25
| Fuel | 1 | LS | 1300 | 1300 | 25% | 960 | 960
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
19 | 14-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 24500 |  |  | 18921.23
| Labor | 1 | LS | 8300 | 8300 | 18% | 6790.48 | 6790.48
| Materials | 1 | LS | 13400 | 13400 | 25% | 9993.5 | 9993.5
| Equipment | 1 | LS | 1200 | 1200 | 18% | 960 | 960
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 300 | 300 | 18% | 217.25 | 217.25
| Fuel | 1 | LS | 1300 | 1300 | 25% | 960 | 960
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
20 | 30-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 95400 |  |  | 72909.49
| Labor | 1 | LS | 20400 | 20400 | 18% | 16662.24 | 16662.24
| Materials | 1 | LS | 75000 | 75000 | 25% | 56247.25 | 56247.25
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
21 | 36-inch Buried Service Butterfly Valve Assembly | Quantity | Unit | Unit Price | 94200 |  |  | 72156.46
| Labor | 1 | LS | 22300 | 22300 | 18% | 18240.96 | 18240.96
| Materials | 1 | LS | 71500 | 71500 | 25% | 53592 | 53592
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 400 | 400 | 18% | 323.5 | 323.5
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
22 | 2-inch Underground Combination Air Valve Assembly | Quantity | Unit | Unit Price | 56000 |  |  | 43662.44
| Labor | 1 | LS | 24900 | 24900 | 18% | 20371.44 | 20371.44
| Materials | 1 | LS | 30900 | 30900 | 25% | 23170 | 23170
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 200 | 200 | 18% | 121 | 121
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
23 | 3-inch Underground Combination Air Valve Assembly | Quantity | Unit | Unit Price | 65700 |  |  | 51317.44
| Labor | 1 | LS | 24900 | 24900 | 18% | 20371.44 | 20371.44
| Materials | 1 | LS | 34600 | 34600 | 25% | 25926 | 25926
| Equipment | 1 | LS | 100 | 100 | 18% | 60 | 60
| Subcontractors | 1 | LS | 800 | 800 | 18% | 640 | 640
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 5300 | 5300 | 18% | 4320 | 4320
24 | 6-inch Underground Combination Air Valve Assembly | Quantity | Unit | Unit Price | 61300 |  |  | 46307.36
| Labor | 1 | LS | 6300 | 6300 | 18% | 5092.86 | 5092.86
| Materials | 1 | LS | 53600 | 53600 | 25% | 40180 | 40180
| Equipment | 1 | LS | 800 | 800 | 18% | 600 | 600
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 600 | 600 | 18% | 434.5 | 434.5
25 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe (Materials) | Quantity | Unit | Unit Price | 159600 |  |  | 119700
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 159600 | 159600 | 25% | 119700 | 119700
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
26 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Open Cut Installation) | Quantity | Unit | Unit Price | 205800 |  |  | 167240.6
| Labor | 1 | LS | 76900 | 76900 | 18% | 62985.6 | 62985.6
| Materials | 1 | LS | 0 | 0 | 25% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 54900 | 54900 | 18% | 45000 | 45000
| Rental | 1 | LS | 54800 | 54800 | 18% | 44855 | 44855
| Fuel | 1 | LS | 19200 | 19200 | 25% | 14400 | 14400
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
27 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Annular Space Backfill) | Quantity | Unit | Unit Price | 83000 |  |  | 68000
| Labor | 1 | LS | 0 | 0 | 18% | 0 | 0
| Materials | 1 | LS | 0 | 0 | 25% | 0 | 0
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 83000 | 83000 | 18% | 68000 | 68000
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
28 | Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Cathodic Protection System) | Quantity | Unit | Unit Price | 43600 |  |  | 34329.6
| Labor | 1 | LS | 17700 | 17700 | 18% | 14479.1 | 14479.1
| Materials | 1 | LS | 17200 | 17200 | 25% | 12900 | 12900
| Equipment | 1 | LS | 2200 | 2200 | 18% | 1800 | 1800
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 4100 | 4100 | 18% | 3350.5 | 3350.5
| Fuel | 1 | LS | 2400 | 2400 | 25% | 1800 | 1800
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
29 | Valve Cathodic Protection (Lat DE) | Quantity | Unit | Unit Price | 35600 |  |  | 28113.8
| Labor | 1 | LS | 20100 | 20100 | 18% | 16413.8 | 16413.8
| Materials | 1 | LS | 14000 | 14000 | 25% | 10500 | 10500
| Equipment | 1 | LS | 1500 | 1500 | 18% | 1200 | 1200
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
30 | Valve Cathodic Protection Test Station (Lat DE) | Quantity | Unit | Unit Price | 43200 |  |  | 33913.8
| Labor | 1 | LS | 20100 | 20100 | 18% | 16413.8 | 16413.8
| Materials | 1 | LS | 18200 | 18200 | 25% | 13600 | 13600
| Equipment | 1 | LS | 3700 | 3700 | 18% | 3000 | 3000
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 1200 | 1200 | 25% | 900 | 900
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
31 | Flange Insulation Kits (Lat DE and Lat DE-1) | Quantity | Unit | Unit Price | 17600 |  |  | 13460.5
| Labor | 1 | LS | 4800 | 4800 | 18% | 3860.5 | 3860.5
| Materials | 1 | LS | 12800 | 12800 | 25% | 9600 | 9600
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
32 | Flange Insulation Cathodic Protection Test Station (Lat DE) | Quantity | Unit | Unit Price | 86600 |  |  | 67896.96
| Labor | 1 | LS | 34000 | 34000 | 18% | 27816.96 | 27816.96
| Materials | 1 | LS | 43200 | 43200 | 25% | 32400 | 32400
| Equipment | 1 | LS | 9400 | 9400 | 18% | 7680 | 7680
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 0 | 0 | 25% | 0 | 0
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
33 | Color Coded Marker Posts | Quantity | Unit | Unit Price | 25200 |  |  | 19966.64
| Labor | 1 | LS | 12900 | 12900 | 18% | 10558.44 | 10558.44
| Materials | 1 | LS | 6600 | 6600 | 25% | 4908.2 | 4908.2
| Equipment | 1 | LS | 3700 | 3700 | 18% | 3000 | 3000
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 0 | 0 | 18% | 0 | 0
| Fuel | 1 | LS | 2000 | 2000 | 25% | 1500 | 1500
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
34 | Hydrostatic Pressure Testing (30-inch Lateral DE-1-A and Connections) | Quantity | Unit | Unit Price | 55900 |  |  | 45085.3
| Labor | 1 | LS | 42900 | 42900 | 18% | 35112.8 | 35112.8
| Materials | 1 | LS | 6700 | 6700 | 25% | 5000 | 5000
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 3900 | 3900 | 18% | 3172.5 | 3172.5
| Fuel | 1 | LS | 2400 | 2400 | 25% | 1800 | 1800
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
35 | Hydrostatic Pressure Testing (36-inch Lateral DE-1 and Connections) | Quantity | Unit | Unit Price | 48800 |  |  | 39290.1
| Labor | 1 | LS | 35800 | 35800 | 18% | 29317.6 | 29317.6
| Materials | 1 | LS | 6700 | 6700 | 25% | 5000 | 5000
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 3900 | 3900 | 18% | 3172.5 | 3172.5
| Fuel | 1 | LS | 2400 | 2400 | 25% | 1800 | 1800
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0
36 | Hydrostatic Pressure Testing (42-inch Lateral DE and Connections) | Quantity | Unit | Unit Price | 79700 |  |  | 63921.4
| Labor | 1 | LS | 53700 | 53700 | 18% | 43976.4 | 43976.4
| Materials | 1 | LS | 13400 | 13400 | 25% | 10000 | 10000
| Equipment | 1 | LS | 0 | 0 | 18% | 0 | 0
| Subcontractors | 1 | LS | 0 | 0 | 18% | 0 | 0
| Rental | 1 | LS | 7800 | 7800 | 18% | 6345 | 6345
| Fuel | 1 | LS | 4800 | 4800 | 25% | 3600 | 3600
| Other | 1 | LS | 0 | 0 | 18% | 0 | 0

## Bid Bond
| 30% | buffer for bid bond (dependent on confidence in all bid items)
Job Cost Breakdown | Totals
Labor | 892812.05
Equipment Rental | 194902.89
Subs | 328806.4
Material | 2947692.787
Overhead | 459204.8727
Profit | 1520753.2502
Other | 249761.85
Total Uncompleted Work | 6593934.1
| 5092935 | Estimate Project Total (for Bond, use a nice round number based on the "total uncompleted work" above)
| 10% | Bid Bond % (see specs)
| 3.05% | Performance Bond Premium %
3.062%

## Bid Item 1
[8 empty] | Bid Item Total | 42209.01 | OUR COST
Lateral DE Connection (36-inch Steel at STA 10+00)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 1 | VENDOR 2 | Total | COMMENT/NOTES
| Mobilization/Demobilization | [7 empty] | 0
1 | Mobilization |  | 0 |  | 3500 |  |  |  | 0
2 | Demobilization |  | 0 |  | 3500 |  |  |  | 0
3 | [8 empty] | 0
Add More | [8 empty] | 0
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More | [8 empty] | 0
| Materials | [7 empty] | 25200
1 | [8 empty] | 0
2 | 42" x 36" Steel Reducer PE x FLG |  | 1 | ea | 23700 |  |  |  | 23700
3 | 42" Full Face Flange Gasket |  | 1 | ea | 100 |  |  |  | 100
4 | 42" Flg x Flg Bolt kit |  | 1 | ea | 700 |  |  |  | 700
5 | 36" Flg Gasket |  | 1 | ea | 100 |  |  |  | 100
6 | 36" Flg x Flg Bolt Kit |  | 1 | ea | 600 |  |  |  | 600
7
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 6000
1 | Coating |  | 1 | EA | 6000 |  |  |  | 6000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1614.85
1 | 85K Excavator |  | 0.15 | Month | 6054 |  |  |  | 908.1 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.45 | Month | 605 |  |  |  | 272.25
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other (may sometimes include Bonds and Insurance) | [7 empty] | 550
1 | Temporary Fittings |  | 1 | EA | 550 |  |  |  | 550
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 2
[8 empty] | Bid Item Total | 17148.56 | OUR COST
Lateral DE-B Connection (12-inch Asbestos-Cement at STA 34+29.21)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 11738.96
1 | Labor Lead |  | 24 | HR | 74.69 |  |  |  | 1792.56 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 72 | HR | 71.69 |  |  |  | 5161.68 | Assumes # of helpers to crew lead as outlined on "Bid Schedule" tab.
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 24 | HR | 76.71 |  |  |  | 1841.04
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 16 | HR | 87.69 |  |  |  | 1403.04
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 1678.25
1 | 42" x 42" x 12" CMLC Tee |  | 0 | ea | 25000 |  |  |  | 0
2 | 12" Flange Adap |  | 1 | ea | 487.25 |  |  |  | 487.25
3 | PVC PIPE 12" C900 DR25 |  | 20 | ea | 20 |  |  |  | 400
4 | 12" Hymax coupler from PVC to AC |  | 1 | ea | 791 |  |  |  | 791
5
6
7
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1741.35
1 | 85K Excavator |  | 0.15 | Month | 6054 |  |  |  | 908.1 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.15 | Month | 4345 |  |  |  | 651.75 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.3 | Month | 605 |  |  |  | 181.5
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 550
1 | Temporary Caps |  | 1 | EA | 550 |  |  |  | 550
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 3
[8 empty] | Bid Item Total | 19085.73 | OUR COST
Lateral DE-1 Connection (27-inch Steel at STA 35+94.05)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 8281.06
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 10 | HR | 87.69 |  |  |  | 876.9
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 6653.77
1 | Steel reducer 36" FCA x 28" FLG |  | 1 | ea | 2098.77 |  |  |  | 2098.77
2 | Steel CL-D Flange 28" |  | 1 | ea | 355 |  |  |  | 355
3 | SS Bolt kit 28" |  | 1 | ea | 2000 |  |  |  | 2000
4 | Gasket 28" |  | 1 | ea | 200 |  |  |  | 200
5 | Concrete |  | 1 | ea | 2000 |  |  |  | 2000
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
11 | [8 empty] | 0
12 | [8 empty] | 0
13 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 1000
1 | Coating |  | 1 | ea | 1000 |  |  |  | 1000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1160.9
1 | 85K Excavator |  | 0.1 | Month | 6054 |  |  |  | 605.4 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 550
1 | Temporary Fittings |  | 1 | EA | 550 |  |  |  | 550
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 4
[8 empty] | Bid Item Total | 32280.74 | OUR COST
DE-1 BPS Connection (18-inch Steel at STA 10+74.99)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 11983.14
1 | Labor Lead |  | 24 | HR | 74.69 |  |  |  | 1792.56 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 72 | HR | 71.69 |  |  |  | 5161.68 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 24 | HR | 96.29 |  |  |  | 2310.96
4 | Driver |  | 24 | HR | 76.71 |  |  |  | 1841.04
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 10 | HR | 87.69 |  |  |  | 876.9
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 16456.75
1 | Wye 30" x 30" x 18" MJ |  | 1 | ea | 10000 |  |  |  | 10000
2 | PVC PIPE C900 18" DR25 |  | 44 | FT | 31 |  |  |  | 1364
3 | Steel Flange 18" CL-d |  | 1 | ea | 150 |  |  |  | 150
4 | 18" FCA flange x Reinforced |  | 1 | ea | 1392.75 |  |  |  | 1392.75
5 | Bolt kit 18" SS FxF |  | 1 | ea | 1000 |  |  |  | 1000
6 | Temporary Fittings |  | 1 | EA | 550 |  |  |  | 550
7 | Concrete |  | 1 | ea | 2000 |  |  |  | 2000
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1680.85
1 | 85K Excavator |  | 0.15 | Month | 6054 |  |  |  | 908.1 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.15 | Month | 4345 |  |  |  | 651.75 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 2160
1 | Diesel |  | 360 | Gal | 6 |  |  |  | 2160
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0 | Hard hats, etc.
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 5
[8 empty] | Bid Item Total | 24203.56 | OUR COST
Lateral DE-1-A-1 Connection (15-inch Asbestos-Cement at STA 50+22.34)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 15638.5
1 | Tee 30" x 30" x 14" Restrained x FLG |  | 1 | ea | 10000 |  |  |  | 10000
2 | pvc pipe c900 14" C900 DR25 |  | 20 | ft | 25 |  |  |  | 500
3 | DI coupler 14" PVC x 15" AC Hymax |  | 1 | ea | 4588.5 |  |  |  | 4588.5
4 | Temp Fittings |  | 1 | ea | 550 |  |  |  | 550
5
6
7
8
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1160.9
1 | 85K Excavator |  | 0.1 | Month | 6054 |  |  |  | 605.4 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  | 0 | Gal | 6 |  |  |  | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0 | Month
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 6
[8 empty] | Bid Item Total | 18649.31 | OUR COST
Lateral DE-1-A Connection (21-inch Asbestos-Cement at STA 51+04.05)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 7404.16
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 8644.25
1 | 30" x 20" Reducer Restrained Hymax |  | 1 | ea | 6000 |  |  |  | 6000
2 | pvc pipe C900 DR25 20" |  | 20 | ft | 35 |  |  |  | 700
3 | Restrained coupling 20" PVC x 21" AC Hymax |  | 1 | ea | 944.25 |  |  |  | 944.25
4 | concrete |  | 1 | ea | 1000 |  |  |  | 1000
5 | Temp Fittings |  | 1 | ea | 550
6
7
8
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1160.9
1 | 85K Excavator |  | 0.1 | Month | 6054 |  |  |  | 605.4 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 7
[8 empty] | Bid Item Total | 52821.26 | OUR COST
Removal and Disposal of Existing Laterals (Lat DE, Lat DE-1, Lat DE-1-A, and BPS Steel Pipe on C-101, C-301, C-302, C-304, C-305, C-402, C-403)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES | 42 | 57
| Labor | [7 empty] | 25018.56 |  | 36 | 107
1 | Labor Lead |  | 48 | HR | 74.69 |  |  |  | 3585.12 | Input Prevailing Wage rates on "Prevailing Wage" tab. | 27 | 76
2 | Laborer |  | 144 | HR | 71.69 |  |  |  | 10323.36 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab | 30 | 30
3 | Operator |  | 48 | HR | 96.29 |  |  |  | 4621.92 |  | 24 | 205 | (53 AC)
4 | Driver |  | 48 | HR | 76.71 |  |  |  | 3682.08
5 | Landscaper |  |  | HR | 0 |  |  |  | 0 |  |  | 475
6 | Pipefitter |  | 32 | HR | 87.69 |  |  |  | 2806.08
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 15000
1 | Plugs |  | 15 | ea | 1000 |  |  |  | 15000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5
6
7
8
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 3482.7
1 | 85K Excavator |  | 0.3 | Month | 6054 |  |  |  | 1816.2 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.3 | Month | 4345 |  |  |  | 1303.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.6 | Month | 605 |  |  |  | 363
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 4320
1 | Diesel |  | 720 | Gal | 6 |  |  |  | 4320
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 5000
1 | Disposal Fee |  | 2 | TRKs | 2500 |  |  |  | 5000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 8
[8 empty] | Bid Item Total | 33502.53 | OUR COST
Removal and Disposal of Existing Laterals and Turnout Connections (Asbestos Cement Pipe on C-302 and C-305)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3702.08
1 | Labor Lead |  | 8 | HR | 74.69 |  |  |  | 597.52 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 71.69 |  |  |  | 1720.56 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 96.29 |  |  |  | 770.32
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 12000
1 | Plugs |  | 12 |  | 1000 |  |  |  | 12000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1500
1 | Semi Truck |  | 1 | day | 1500 |  |  |  | 1500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 580.45
1 | 85K Excavator |  | 0.05 | Month | 6054 |  |  |  | 302.7 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.05 | Month | 4345 |  |  |  | 217.25 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.1 | Month | 605 |  |  |  | 60.5
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 720
1 | Diesel |  | 120 | Gal | 6 |  |  |  | 720
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 15000
1 | Disposal Fee |  | 1 | ea | 15000 |  |  |  | 15000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 9
[8 empty] | Bid Item Total | 5388.85 | OUR COST
Removal and Disposal of Existing Turnout Connections (PVC Pipe on C-402 and C-403)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3088.4
1 | Labor Lead |  | 8 | HR | 74.69 |  |  |  | 597.52 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 24 | HR | 71.69 |  |  |  | 1720.56 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 8 | HR | 96.29 |  |  |  | 770.32
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 500
1 | Misc Material |  | 1 | EA | 500 |  |  |  | 500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 580.45
1 | 85K Excavator |  | 0.05 | Month | 6054 |  |  |  | 302.7 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.05 | Month | 4345 |  |  |  | 217.25 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.1 | Month | 605 |  |  |  | 60.5
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 720
1 | Diesel |  | 120 | Gal | 6 |  |  |  | 720
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 500
1 | DISPOSAL FEE |  | 1 | EA | 500 |  |  |  | 500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 10
[8 empty] | Bid Item Total | 18225.72 | OUR COST
Removal and Disposal of Existing Marker Posts and Cathodic Protection Test Stations
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 10185.72
1 | Labor Lead |  | 24 | HR | 74.69 |  |  |  | 1792.56 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 72 | HR | 71.69 |  |  |  | 5161.68 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 24 | HR | 96.29 |  |  |  | 2310.96
4 | Driver |  | 12 | HR | 76.71 |  |  |  | 920.52
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 500
1 | Misc Material |  | 1 | ea | 500 |  |  |  | 500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 2880
1 | Mini Excavtor |  | 24 | HR | 60 |  |  |  | 1440
2 | Trucking |  | 12 | HR | 120 |  |  |  | 1440
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 2160
1 | Diesel |  | 360 | Gal | 6 |  |  |  | 2160
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 2500
1 | Disposal Fee |  | 1 | ea | 2500 |  |  |  | 2500
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 11
[8 empty] | Bid Item Total | 668072.8 | OUR COST
30-inch PVC Pipe (Lateral DE-1-A)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 89448
1 | Labor Lead |  | 160 | HR | 74.69 |  |  |  | 11950.4 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 480 | HR | 71.69 |  |  |  | 34411.2 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 320 | HR | 96.29 |  |  |  | 30812.8
4 | Driver |  | 160 | HR | 76.71 |  |  |  | 12273.6
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 483969.8
1 | PVC PIPE C900 DR25 30" |  | 4105 | ft | 105.76 |  |  |  | 434144.8
2 | Elbow 45° 30" Hymax Restrained |  | 10 | ea | 3982.5 |  |  |  | 39825
3 | Concrete |  | 10 | ea | 1000 |  |  |  | 10000
4 | [8 empty] | 0
5
6
7
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 46655
1 | 120K Excavator |  | 1 | Month | 13100 |  |  |  | 13100 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 1 | Month | 6055 |  |  |  | 6055 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 1 | Month | 4345 |  |  |  | 4345
4 | Compaction |  | 4 | Month | 605 |  |  |  | 2420
| Shoring |  | 0.5 | Months | 35000 |  |  |  | 17500
Add More | Telehandler |  | 1 | Month | 3235 |  |  |  | 3235
End | [8 empty] | 0
| Fuel | [7 empty] | 48000
1 | Diesel |  | 8000 | Gal | 6 |  |  |  | 48000
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 12
[8 empty] | Bid Item Total | 563360.82 | OUR COST
36-inch PVC Pipe (Lateral DE-1)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 62613.6
1 | Labor Lead |  | 112 | HR | 74.69 |  |  |  | 8365.28 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 336 | HR | 71.69 |  |  |  | 24087.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 224 | HR | 96.29 |  |  |  | 21568.96
4 | Driver |  | 112 | HR | 76.71 |  |  |  | 8591.52
5 | Landscaper |  |  | HR | 0 |  |  |  | 0 |  | 217.0947
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 452569.72 |  | 14
1 | PVC PIPE C900 DR25 36" |  | 2595 | ft | 155.04 |  |  |  | 402328.8
2 | Elbow 45* MJ |  | 4 | ea | 5821.75 |  |  |  | 23287
3 | Concrete |  | 4 | ea | 1000 |  |  |  | 4000
4 | Bell Joint Restraints |  | 8 |  | 2869.24 |  |  |  | 22953.92
5
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 14577.5
1 | 120K Excavator |  | 0.5 | Month | 13100 |  |  |  | 6550 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.5 | Month | 6055 |  |  |  | 3027.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.5 | Month | 4345 |  |  |  | 2172.5
4 | Compaction |  | 2 | Month | 605 |  |  |  | 1210
Add More | Telehandler |  | 0.5 | Month | 3235 |  |  |  | 1617.5
End | [8 empty] | 0
| Fuel | [7 empty] | 33600
1 | Diesel |  | 5600 | Gal | 6 |  |  |  | 33600
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 13
[8 empty] | Bid Item Total | 937177 | OUR COST
42-inch Steel Pipe (Lateral DE)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 48422
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 240 | HR | 71.69 |  |  |  | 17205.6 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 80 | HR | 96.29 |  |  |  | 7703.2
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 200 | HR | 87.69 |  |  |  | 17538
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 740652
1 | 42" CML&C Pipe |  | 2544 | ft | 283 |  |  |  | 719952
2 | Mortar Diapers |  | 128 | ea | 150 |  |  |  | 19200
3 | Welding Consumeables |  | 1 | ea | 1500 |  |  |  | 1500
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 132288
1 | Unload, String, Excavate, Set, Mortar & Backfill |  | 2544 | ft | 52 | Superior Ag |  |  | 132288
2
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 10055
1 | Truck & Welder |  | 160 | HR | 25 |  |  |  | 4000 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 1 | Month | 6055 |  |  |  | 6055 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0 | Month | 4345 |  |  |  | 0
4 | Compaction |  | 0 | Month | 605 |  |  |  | 0
Add More | Handling |  | 0 | Month | 4500 |  |  |  | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 5760
1 | Diesel |  | 960 | Gal | 6 |  |  |  | 5760
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 14
[8 empty] | Bid Item Total | 12599.1 | OUR COST
Connection to Turnout 14D (14-inch PVC at STA 17+67.77)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 8807.2
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 16 | HR | 87.69 |  |  |  | 1403.04
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 1191
1 | 42" x 42" x 12" Tee CML&C comp |  |  | ea |  |  |  |  | 0
2 | PVC PIPE C900 DR25 12" |  | 20 | FT | 20 |  |  |  | 400
3 | Coupler 12" PVC x PVC Hymax |  | 1 | ea | 791 |  |  |  | 791
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1160.9
1 | 85K Excavator |  | 0.1 | Month | 6054 |  |  |  | 605.4 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 15
[8 empty] | Bid Item Total | 10469.22 | OUR COST
Connection to Turnout 12D (10-inch Asbestos-Cement at STA 34+14.45)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 6878.32
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 8 | HR | 87.69 |  |  |  | 701.52
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 990
1 | 42" x 42" x 10" Tee CML&C comp |  | 0 | ea | 20000 |  |  |  | 0
2 | PVC PIPE C900 DR25 10" |  | 20 | FT | 16 |  |  |  | 320
3 | Coupler 10" PVC x AC Hymax |  | 1 | ea | 670 |  |  |  | 670
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1160.9
1 | 85K Excavator |  | 0.1 | Month | 6054 |  |  |  | 605.4 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 16
[8 empty] | Bid Item Total | 19767.7 | OUR COST
Connection to Turnout 28D (10-inch PVC at STA 24+42.80)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 6176.8
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 10990
1 | 30" x 30" x 10" Tee restrained jt x FLG |  | 1 | ea | 10000 |  |  |  | 10000
2 | PVC PIPE C900 DR25 10" |  | 20 | FT | 16 |  |  |  | 320
3 | Coupler 10" PVC x AC Hymax |  | 1 | ea | 670 |  |  |  | 670
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1160.9
1 | 85K Excavator |  | 0.1 | Month | 6054 |  |  |  | 605.4 | For equipment rates see this spreadsheet:
2 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1440
1 | Diesel |  | 240 | Gal | 6 |  |  |  | 1440
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 17
[8 empty] | Bid Item Total | 47152.53 | OUR COST
10-inch Buried Service Butterfly Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 12967.28
1 | Labor Lead |  | 32 | HR | 74.69 |  |  |  | 2390.08 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 96 | HR | 71.69 |  |  |  | 6882.24 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 32 | HR | 96.29 |  |  |  | 3081.28
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 30128
1 | 10" Hymax Coup x FLG |  | 4 | ea | 670 |  |  |  | 2680
2 | 10" Valmatic BFV |  | 4 | ea | 6037 | B&K |  |  | 24148 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
3 | 10" SS Bolt kit FxF |  | 8 | ea | 300 |  |  |  | 2400
4 | 10" Gasket |  | 8 | ea | 50 |  |  |  | 400
Add More | Concrete |  | 1 | ea | 500 |  |  |  | 500
End | [8 empty] | 0
| Equipment | [7 empty] | 1920
1 | Mini Excavator |  | 32 | hrs | 60 |  |  |  | 1920
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 217.25
1 | Water Truck |  | 0.05 | Month | 4345 |  |  |  | 217.25 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1920
1 | Diesel |  | 320 | GAL | 6 |  |  |  | 1920
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 18
[8 empty] | Bid Item Total | 20904.73 | OUR COST
12-inch Buried Service Butterfly Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 6790.48
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 11977
1 | 12" Hymax Coup x FLG |  | 1 | ea | 791 |  |  |  | 791
2 | 12" Valmatic BFV |  | 1 | ea | 6386 | B&K |  |  | 6386 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
3 | 12" SS Bolt kit FxF |  | 2 | ea | 350 |  |  |  | 700
4 | 12" Gasket |  | 2 | ea | 50 |  |  |  | 100
Add More | Misc |  | 1 |  | 4000 |  |  |  | 4000
End | [8 empty] | 0
| Equipment | [7 empty] | 960
1 | Mini Excavator |  | 16 | hrs | 60 |  |  |  | 960
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 217.25
1 | Water Truck |  | 0.05 | Month | 4345 |  |  |  | 217.25 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 960
1 | Diesel |  | 160 | GAL | 6 |  |  |  | 960
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 19
[8 empty] | Bid Item Total | 18921.23 | OUR COST
14-inch Buried Service Butterfly Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 6790.48
1 | Labor Lead |  | 16 | HR | 74.69 |  |  |  | 1195.04 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 48 | HR | 71.69 |  |  |  | 3441.12 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 16 | HR | 96.29 |  |  |  | 1540.64
4 | Driver |  | 8 | HR | 76.71 |  |  |  | 613.68
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 9993.5
1 | 14" Hymax Coup x FLG |  | 1 | ea | 3930.5 |  |  |  | 3930.5
2 | 14" Valmatic BFV |  | 1 | ea | 5163 |  |  |  | 5163 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
3 | 14" SS Bolt kit FxF |  | 2 | ea | 400 |  |  |  | 800
4 | 14" Gasket |  | 2 | ea | 50 |  |  |  | 100
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 960
1 | Mini Excavator |  | 16 | hrs | 60 |  |  |  | 960
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 217.25
1 | Water Truck |  | 0.05 | Month | 4345 |  |  |  | 217.25 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 960
1 | Diesel |  | 160 | GAL | 6 |  |  |  | 960
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 20
[8 empty] | Bid Item Total | 83012.49 | OUR COST
30-inch BFV Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 16662.24
1 | Labor Lead |  | 32 | HR | 74.69 |  |  |  | 2390.08 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 96 | HR | 71.69 |  |  |  | 6882.24 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 64 | HR | 96.29 |  |  |  | 6162.56
4 | Driver |  | 16 | HR | 76.71 |  |  |  | 1227.36
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 56247.25
1 | 36" x 36" x 30" Restrained X FLG |  | 1 | ea | 10000 |  |  |  | 10000
2 | 30" Valmatic BFV |  | 1 | ea | 35268 |  |  |  | 35268 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
| 30" FLG X Coup Hymax |  | 1 | ea | 3379.25 |  |  |  | 3379.25
3 | 30" SS Bolt kit FxF |  | 2 | ea | 3000 |  |  |  | 6000
4 | 30" Gasket |  | 2 | ea | 200 |  |  |  | 400
Add More | Concrete |  | 1 | EA | 1200 |  |  |  | 1200
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 2423
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.25 | Month | 6055 |  |  |  | 1513.75 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.25 | Month | 605 |  |  |  | 151.25
Add More | Telehandler |  | 0.1 | Month | 3235 |  |  |  | 323.5
End | [8 empty] | 0
| Fuel | [7 empty] | 7680
1 | Diesel |  | 1280 | Gal | 6 |  |  |  | 7680
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 21
[8 empty] | Bid Item Total | 81935.96 | OUR COST
36" BFV Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 18240.96
1 | Labor Lead |  | 32 | HR | 74.69 |  |  |  | 2390.08 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 96 | HR | 71.69 |  |  |  | 6882.24 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 64 | HR | 96.29 |  |  |  | 6162.56
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 32 | HR | 87.69 |  |  |  | 2806.08
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 53592
1 | 42" x 42" x 36" Steel Tee X FLG |  | 0 | ea | 30000 |  |  |  | 0
2 | 36" Valmatic BFV |  | 1 | ea | 37052 | B&K |  |  | 37052 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
3 | 36" FLG X Coup Hymax |  | 1 | ea | 4840 |  |  |  | 4840
4 | 36" SS Bolt kit FxF |  | 2 | ea | 5000 |  |  |  | 10000
| 36" Gasket |  | 2 | ea | 250 |  |  |  | 500
Add More | Concrete |  | 1 | EA | 1200 |  |  |  | 1200
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 2423
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.25 | Month | 6055 |  |  |  | 1513.75 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.25 | Month | 605 |  |  |  | 151.25
Add More | Telehandler |  | 0.1 | Month | 3235 |  |  |  | 323.5
End | [8 empty] | 0
| Fuel | [7 empty] | 7680
1 | Diesel |  | 1280 | Gal | 6 |  |  |  | 7680
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 22
[8 empty] | Bid Item Total | 47262.44 | OUR COST
2-inch Underground Combination Air Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 20371.44
1 | Labor Lead |  | 48 | HR | 74.69 |  |  |  | 3585.12 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 144 | HR | 71.69 |  |  |  | 10323.36 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 48 | HR | 96.29 |  |  |  | 4621.92
4 | Driver |  | 24 | HR | 76.71 |  |  |  | 1841.04
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 23170
1 | 30" Tapping Sleeve with 2" threaded outlet |  | 1 | ea | 4000 |  |  |  | 4000
| 36" Tapping Sleeve with 2" threaded outlet |  | 1 | ea | 5000 |  |  |  | 5000
2 | 2" Galv S40 Welded Steel Pipe Nipple Long TBE |  | 2 | ea | 20 |  |  |  | 40
3 | 2" Gate Valve, Stockham Fig 120 |  | 2 | ea | 200 |  |  |  | 400
4 | 2" Galv S40 Welded Steel Pipe Nipple Short TBE |  | 2 | ea | 15 |  |  |  | 30
5 | 2" Val-Matic Series 201CSSA |  | 2 | ea | 2230 |  |  |  | 4460 | Val-Matic Combination Air Release Valve for Water, Cast Iron Body, 316 Stainless Steel Trim & Float, Threaded Screen Hood, Buna-N Seat, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 300 PSI CWP. ***IF regulated exhaust is requred Please add $377.00 Each.***
6 | 2" Galv Sch 40 90* Street |  | 2 | ea | 20 |  |  |  | 40
7 | 2" Prefabricated fittings with integral ss screen |  | 2 | ea | 100 |  |  |  | 200
8 | Concrete Box with manhole - traffic rated - Page 40 in plans |  | 2 | ea | 4000 |  |  |  | 8000
9 | gravel & geotech |  | 2 | ea | 500 |  |  |  | 1000
10 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 640
1 | Mini Ex |  | 8 | HR | 80 |  |  |  | 640
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1161
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.1 | Month | 6055 |  |  |  | 605.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.2 | Month | 605 |  |  |  | 121
Add More | Telehandler |  | 0 | Month | 3235 |  |  |  | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1920
1 | Diesel |  | 320 | Gal | 6 |  |  |  | 1920
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 23
[8 empty] | Bid Item Total | 52478.94 | OUR COST
3-inch Underground Combination Air Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 20371.44
1 | Labor Lead |  | 48 | HR | 74.69 |  |  |  | 3585.12 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 144 | HR | 71.69 |  |  |  | 10323.36 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 48 | HR | 96.29 |  |  |  | 4621.92
4 | Driver |  | 24 | HR | 76.71 |  |  |  | 1841.04
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 25926
1 | 30" Tapping Sleeve with 3" threaded outlet |  | 1 | ea | 4000 |  |  |  | 4000
2 | 36" Tapping Sleeve with 3" threaded outlet |  | 1 | ea | 5000 |  |  |  | 5000
3 | 3" Galv S40 Welded Steel Pipe Nipple Long TBE |  | 2 | ea | 30 |  |  |  | 60
4 | 3" Gate Valve, Stockham Fig 120 |  | 2 | ea | 250 |  |  |  | 500
| 3" Galv S40 Welded Steel Pipe Nipple Short TBE |  | 2 | ea | 20 |  |  |  | 40
| 3" Val-Matic Series 201CSSA |  | 2 | ea | 3983 |  |  |  | 7966 | Val-Matic Combination Air Release Valve for Water, Cast Iron Body, 316 Stainless Steel Trim & Float, Threaded Screen Hood, Buna-N Seat, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 300 PSI CWP. ***IF regulated exhaust is requred Please add $662.00 Each.***
| 3" Galv Sch 40 90* Street |  | 2 | ea | 30 |  |  |  | 60
| 3" Prefabricated fittings with integral ss screen |  | 2 | ea | 150 |  |  |  | 300
| Concrete Box with manhole - traffic rated - Page 40 in plans |  | 2 | ea | 4000 |  |  |  | 8000
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 640
1 | Mini Ex |  | 8 | HR | 80 |  |  |  | 640
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1221.5
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.1 | Month | 6055 |  |  |  | 605.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.3 | Month | 605 |  |  |  | 181.5
Add More | Telehandler |  | 0 | Month | 3235 |  |  |  | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 4320
1 | Diesel |  | 720 | Gal | 6 |  |  |  | 4320
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 24
[8 empty] | Bid Item Total | 47574.36 | OUR COST
6-inch Underground Combination Air Valve Assembly
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 5092.86
1 | Labor Lead |  | 12 | HR | 74.69 |  |  |  | 896.28 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 36 | HR | 71.69 |  |  |  | 2580.84 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 12 | HR | 96.29 |  |  |  | 1155.48
4 | Driver |  | 6 | HR | 76.71 |  |  |  | 460.26
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 40180
1 | 6" Welded Outlet |  | 0 | ea | 8000 |  |  |  | 0
2 | 6" DI elbow 90* FLG x FLG |  | 2 | ea | 400 |  |  |  | 800
3 | Bolt Kit 6" SS FLG x FLG |  | 8 | ea | 150 |  |  |  | 1200
4 | 6" DI Flange Adap |  | 4 | ea | 400 |  |  |  | 1600
| 6" DI Pipe |  | 20 | ft | 34 |  |  |  | 680
| 6" Valmatic BFV FLG |  | 2 | ea | 4335 |  |  |  | 8670 | Val-Matic Series 2000 Butterfly Valve, AWWA Class 150B/125# Flanged Ends, Cast Iron Body, 304 Stainless Steel Shaft, Ductile Iron Disc w/ Buna-N Seat, 316 Stainless Steel Body Seat, 316 Stainless Streel Bolts, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 150 PSI CWP.
| 6" DI Flange |  | 2 | ea | 300 |  |  |  | 600
| 6" DI Flange Spacer |  | 1 | ea | 200 |  |  |  | 200
| 6" Val-Matic Series 201CSSA |  | 1 | ea | 11430 |  |  |  | 11430 | Val-Matic Combination Air Release Valve for Water, Cast Iron Body, ANSI Class 125 Flanged Ends, 316 Stainless Steel Trim & Float, Threaded Screen Hood, Buna-N Seat, Lined & Coated with 12-20 mils Fusion Bonded Epoxy, 300 PSI CWP. ***IF regulated exhaust is requred Please add $1,985.00 Each.***
| Concrete Structures |  | 1 | ea | 6000 |  |  |  | 6000
| Enclosure |  | 1 | ea | 2000 |  |  |  | 2000
| Coating |  | 1 | ea | 2000 |  |  |  | 2000
| Misc |  | 1 |  | 5000 |  |  |  | 5000
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 1221.5
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.1 | Month | 6055 |  |  |  | 605.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.3 | Month | 605 |  |  |  | 181.5
Add More | Telehandler |  | 0 | Month | 3235 |  |  |  | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1080
1 | Diesel |  | 180 | Gal | 6 |  |  |  | 1080
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 25
[8 empty] | Bid Item Total | 119700 | OUR COST
Magnolia Avenue Crossing – 58-inch Steel Casing Pipe (Materials)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  |  | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 119700
1 | 58" Steel Pipe |  | 44 | ft | 800 |  |  |  | 35200
2 | Other Casing Materials |  | 1 | ea | 10000 |  |  |  | 10000
3 | Concrete |  | 1 | ea | 6500 |  |  |  | 6500
4 | Spacers |  | 8 | ea | 8500 |  |  |  | 68000
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | Compaction Equipment |  |  | wk | 120 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | Water Truck |  |  | day | 4500 |  |  |  | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | 80K Excavator |  |  | week | 3000 |  |  |  | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | Gal | 6 |  |  |  | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 26
[8 empty] | Bid Item Total | 167240.6 | OUR COST
Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Open Cut Installation)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 62985.6
1 | Labor Lead |  | 120 | HR | 74.69 |  |  |  | 8962.8 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 360 | HR | 71.69 |  |  |  | 25808.4 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 120 | HR | 96.29 |  |  |  | 11554.8
4 | Driver |  | 80 | HR | 76.71 |  |  |  | 6136.8
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  | 120 | HR | 87.69 |  |  |  | 10522.8
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 45000
1 | Saw Cut & Repave |  | 1 | ea | 45000 |  |  |  | 45000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 44855
1 | 120K Excavator |  | 0.5 | Month | 13100 |  |  |  | 6550 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.5 | Month | 6055 |  |  |  | 3027.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.5 | Month | 4345 |  |  |  | 2172.5
4 | Compaction |  | 1 | Month | 605 |  |  |  | 605
| Shoring |  | 0.5 | Month | 50000 |  |  |  | 25000
Add More | Handling |  | 0.5 | Month | 15000 |  |  |  | 7500
End | [8 empty] | 0
| Fuel | [7 empty] | 14400
1 | Diesel |  | 2400 | Gal | 6 |  |  |  | 14400
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 27
[8 empty] | Bid Item Total | 68000 | OUR COST
Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Annular Space Backfill)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 0
1 | Labor Lead |  |  | HR | 74.69 |  |  |  | 0 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 0 | HR | 71.69 |  |  |  | 0 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 68000
1 | Backfill |  | 1 | EA | 68000 |  |  |  | 68000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 28
[8 empty] | Bid Item Total | 34329.6 | OUR COST
Magnolia Avenue Crossing – 58-inch Steel Casing Pipe/42-inch Steel Carrier Pipe (Cathodic Protection System)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 14479.1
1 | Labor Lead |  | 40 | HR | 74.69 |  |  |  | 2987.6 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 120 | HR | 71.69 |  |  |  | 8602.8 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 30 | HR | 96.29 |  |  |  | 2888.7
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 12900
1 | MAGNESIUM ANNODES |  | 4 |  | 1500 |  |  |  | 6000
2 | WIRE/CONDUIT/ETC |  | 1 | EA | 6500 |  |  |  | 6500
3 | BOLLARD |  | 2 | EA | 200 |  |  |  | 400
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1800
1 | MINI EX |  | 30 | HR | 60 |  |  |  | 1800
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 3350.5
1 | 120K Excavator |  | 0 | Month | 13100 |  |  |  | 0 | For equipment rates see this spreadsheet:
2 | 80K Excavator |  | 0.1 | Month | 6055 |  |  |  | 605.5 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | Water Truck |  | 0.1 | Month | 4345 |  |  |  | 434.5
4 | Compaction |  | 0.1 | Month | 605 |  |  |  | 60.5
Add More | Shoring |  | 0 | Month | 50000 |  |  |  | 0
End | Handling |  | 0.5 | Month | 4500 |  |  |  | 2250
1800
1 | Fuel | [7 empty] | 0
2 | Diesel |  | 300 | Gal | 6 |  |  |  | 1800
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 29
[8 empty] | Bid Item Total | 28113.8 | OUR COST
Valve Cathodic Protection (Lat DE)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 16413.8
1 | Labor Lead |  | 50 | HR | 74.69 |  |  |  | 3734.5 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 150 | HR | 71.69 |  |  |  | 10753.5 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 20 | HR | 96.29 |  |  |  | 1925.8
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 10500
1 | MAGNESIUM ANNODES |  | 3 | EA | 1000 |  |  |  | 3000
2 | WIRE/CONDUIT/ETC |  | 3 | EA | 1500 |  |  |  | 4500
3 | Misc Materials |  | 1 | EA | 3000 |  |  |  | 3000
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 1200
1 | MINI EX |  | 20 | HR | 60 |  |  |  | 1200
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel |  |  | GAL |  |  |  |  | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 30
[8 empty] | Bid Item Total | 33913.8 | OUR COST
Valve Cathodic Protection Test Station (Lat DE)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 16413.8
1 | Labor Lead |  | 50 | HR | 74.69 |  |  |  | 3734.5 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 150 | HR | 71.69 |  |  |  | 10753.5 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 20 | HR | 96.29 |  |  |  | 1925.8
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 13600
1 | WIRE/CONDUIT/ETC |  | 3 | EA | 2500 |  |  |  | 7500
2 | BOLLARD |  | 3 | EA | 200 |  |  |  | 600
3 | MISC MATERIAL |  | 1 | ea | 5500 |  |  |  | 5500
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 3000
1 | MINI EX |  | 50 | HR | 60 |  |  |  | 3000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 900
1 | Diesel |  | 150 | GAL | 6 |  |  |  | 900
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 31
[8 empty] | Bid Item Total | 13460.5 | OUR COST
Flange Insulation Kits (Lat DE and Lat DE-1)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 3860.5
1 | Labor Lead |  | 10 | HR | 74.69 |  |  |  | 746.9 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 30 | HR | 71.69 |  |  |  | 2150.7 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 10 | HR | 96.29 |  |  |  | 962.9
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 9600
1 | Flange Gaskets 1/8" Full Face Neoprene |  | 16 |  | 100 |  |  |  | 1600
2 | Insulating sleeves and washers 1/8" thick |  | 16 | EA | 500 |  |  |  | 8000
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 32
[8 empty] | Bid Item Total | 67896.96 | OUR COST
Flange Insulation Cathodic Protection Test Station (Lat DE)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 27816.96
1 | Labor Lead |  | 96 | HR | 74.69 |  |  |  | 7170.24 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 288 | HR | 71.69 |  |  |  | 20646.72 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 32400
1 | WIRE/CONDUIT/ETC |  | 12 | EA | 2500 |  |  |  | 30000
2 | BOLLARD |  | 12 | EA | 200 |  |  |  | 2400
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 7680
1 | MINI EX |  | 96 | HR | 80 |  |  |  | 7680
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 0
1 | Diesel | [7 empty] | 0
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 33
[8 empty] | Bid Item Total | 19966.64 | OUR COST
Color Coded Marker Posts
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 10558.44
1 | Labor Lead |  | 16.5 | HR | 74.69 |  |  |  | 1232.385 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 49.5 | HR | 71.69 |  |  |  | 3548.655 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 60 | HR | 96.29 |  |  |  | 5777.4
4 | Driver |  |  | HR | 76.71 |  |  |  | 0
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 4908.2
1 | 4" Steel Pipe S40 |  | 100 | ft | 15 |  |  |  | 1500
2 | Concrete |  | 1 | ea | 3148.2 |  |  |  | 3148.2
3 | Stickers |  | 13 |  | 20 |  |  |  | 260
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 3000
1 | Mini Excavator |  | 50 | hr | 60 |  |  |  | 3000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 0
1 | [8 empty] | 0 | For equipment rates see this spreadsheet:
2 | [8 empty] | 0 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1500
1 | Diesel |  | 250 | gal | 6 |  |  |  | 1500
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 34
[8 empty] | Bid Item Total | 45085.3 | OUR COST
Hydrostatic Pressure Testing (30-inch Lateral DE-1-A and Connections)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 35112.8
1 | Labor Lead |  | 100 | HR | 74.69 |  |  |  | 7469 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 300 | HR | 71.69 |  |  |  | 21507 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  | 80 | HR | 76.71 |  |  |  | 6136.8
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 5000
1 | Blind Flanges |  | 10 |  | 500 |  |  |  | 5000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 3172.5
1 | Water Truck |  | 0.5 | Month | 4345 |  |  |  | 2172.5 | For equipment rates see this spreadsheet:
2 | Pump |  | 2 | weeks | 500 |  |  |  | 1000 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1800
1 | Diesel |  | 300 | gal | 6 |  |  |  | 1800
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 35
[8 empty] | Bid Item Total | 39290.1 | OUR COST
Hydrostatic Pressure Testing (36-inch Lateral DE-1 and Connections)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 29317.6
1 | Labor Lead |  | 80 | HR | 74.69 |  |  |  | 5975.2 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 240 | HR | 71.69 |  |  |  | 17205.6 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  |  | HR | 96.29 |  |  |  | 0
4 | Driver |  | 80 | HR | 76.71 |  |  |  | 6136.8
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 5000
1 | Blind Flange Material |  | 10 | ea | 500 |  |  |  | 5000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 3172.5
1 | Water Truck |  | 0.5 | Month | 4345 |  |  |  | 2172.5 | For equipment rates see this spreadsheet:
2 | Pump |  | 2 | weeks | 500 |  |  |  | 1000 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 1800
1 | Diesel |  | 300 | gal | 6 |  |  |  | 1800
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0

## 36
[8 empty] | Bid Item Total | 63921.4 | OUR COST
Hydrostatic Pressure Testing (42-inch Lateral DE and Connections)
| ITEM | BID PACKET PAGE | QTY | UNIT | UNIT COST 1 | VENDOR 1 | UNIT COST 2 | VENDOR 2 | Total | COMMENT/NOTES
| Labor | [7 empty] | 43976.4
1 | Labor Lead |  | 120 | HR | 74.69 |  |  |  | 8962.8 | Input Prevailing Wage rates on "Prevailing Wage" tab.
2 | Laborer |  | 360 | HR | 71.69 |  |  |  | 25808.4 | Assumes # of helpers to crew lead as outlined on Bid Schedule tab
3 | Operator |  | 0 | HR | 96.29 |  |  |  | 0
4 | Driver |  | 120 | HR | 76.71 |  |  |  | 9205.2
5 | Landscaper |  |  | HR | 0 |  |  |  | 0
6 | Pipefitter |  |  | HR | 87.69 |  |  |  | 0
7 | Etc |  |  | HR | 0 |  |  |  | 0
8 | Etc |  |  | HR | 0 |  |  |  | 0
Add More |  |  |  | HR |  |  |  |  | 0
| Materials | [7 empty] | 10000
1 | Blind Flange Material |  | 20 | ea | 500 |  |  |  | 10000
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Equipment | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Subcontractors | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Rental | [7 empty] | 6345
1 | Water Truck |  | 1 | Month | 4345 |  |  |  | 4345 | For equipment rates see this spreadsheet:
2 | Pump |  | 4 | weeks | 500 |  |  |  | 2000 | https://laurel-ag.box.com/s/fscobx1vxxwhne2hxnathrnucmlxae6m
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Fuel | [7 empty] | 3600
1 | Diesel |  | 600 | gal | 6 |  |  |  | 3600
2 | Gas | [7 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0
| Other | [7 empty] | 0
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
Add More | [8 empty] | 0
End | [8 empty] | 0